RITTENHOUSE ROAD IMPROVEMENTS

213th Street to Riggs Road

PROJECT NO. A0306

PREPARED BY:

Designer Logo

Date

TECHNICAL SPECIFICATIONS

SPECIAL PROVISIONS

IFB No. XX-XXX

TEMPLATE

TABLE OF CONTENTS

SECTION 101 ABBREVIATIONS AND DEFINITIONS	4

SECTION 104 SCOPE OF WORK 	4

SECTION 105 CONTROL OF WORK	7

SECTION 106 CONTROL OF MATERIALS	19

SECTION 107 LEGAL REGULATIONS AND RESPONSIBILITY TO PUBLIC 	20

SECTION 108 COMMENCEMENT, PROSECTUTION AND PROGRESS	26

SECTION 109 MEASUREMENTS AND PAYMENTS 	28

SECTION 201 CLEARING AND GRUBBING 	30

SECTION 205 ROADWAY EXCAVATION – DRAINAGE 	30

SECTION 215 EARTHWORK 	30

SECTION 220 RIPRAP CONSTRUCTION	31

SECTION 301 SUBGRADE PREPARATION	32

SECTION 310 PLACEMENT AND CONSTRUCTION OF AGGREGATE BASE COURSE	33

SECTION 321 PLACEMENT AND CONSTRUCTION OF ASHPHALT CONCRETE PAVEMENT	34

SECTION 329 TACK COAT	34

SECTION 336 PAVEMENT MATCHING AND SURFACING REPLACEMENT	36

SECTION 340 CONCRETE CURB, GUTTER, SIDEWALK RAMPS, AND DRIVEWAY	37

SECTION 345 ADJUSTING FRAMES, COVERS, VALVE BOXES, WATER METER BOXES	38

SECTION 350 REMOVAL OF EXISTING IMPROVEMENTS	39

SECTION 401 TRAFFIC CONTROL	41

SECTION 405 MONUMENTS	45

SECTION 430 LANDSCAPING AND PLANTING	46

SECTION 460 REMOVAL OF PAVEMENT MARKINGS AND RAISED PAVEMENT MARKERS	50

SECTION 461 PAINTED PAVEMENT MARKINGS	53

SECTION 462 THERMOPLASTIC PAVEMENT MARKINGS	54

SECTION 463 RAISED PAVEMENT MARKERS	55

SECTION 465 TRAFFIC SIGNS	55

SECTION 470 SRP RELATED WORK 	57

SECTION 472 TRAFFIC SIGNAL AND ROADWAY LIGHTING FOUNDATIONS	61

SECTION 474 TRAFFIC SIGNAL POLE INSTALLATION	63

SECTION 475 ELECTRICAL POWER SERVICE AND CONTROLLER CABINET INSTALLATION	63

SECTION 476 SIGNAL INDICATIONS AND MOUNTINGS	64

SECTION 477 INTERSECTION LIGHTING 	65

SECTION 478 ELECTRICAL CONDUCTORS	66

SECTION 483 CLOSED CIRCUIT TELEVISION	67

SECTION 485 VIDEO IMAGE DETECTORS 	68

SECTION 486 COMMUNICATION EQUIPMENT	68

SECTION 505 CONCRETE STRUCTURES 	70

SECTION 508 PREFABRICATED FIRST FLUSH TREATMENT DEVICE 	70

SECTION 520 STEEL AND ALUMINUM HANDRAILS 	71

SECTION 601 TRENCH EXCAVATION, BACKFILLING AND COMPACTION 	71

SECTION 618 IRRIGATION CONSTRUCTION 	72

SECTION 619 STORM DRAIN CULVERTS 	72

PART 100 - GENERAL CONDITIONS

The Town of Queen Creek Design Standards and Procedures Manual available on the internet at

http://www.queencreek.org/Index.aspx?page=625 are a part of these contract documents.

The "Uniform Standard Specifications for Public Works Construction" which are sponsored and distributed by the Maricopa Association of Governments (MAG), and which are hereinafter referred to as the "MAG Standard Specifications," are hereby adopted and a part of these contract documents. Copies of these documents, with revisions, may be obtained at the Maricopa Association of Governments, 302 North 1st Avenue, Phoenix, AZ, 85003 and on the internet at https://www.azmag.gov/Communications/publications.asp. Version 2015 with 2016 and 2017 updates/revisions will be utilized.

Portions of the Maricopa County Department of Transportation 2017 Supplement to the MAG Standard Specifications are also adopted as part of these contract documents. Copies of these documents may be obtained at:

Maricopa County Department of Transportation

2901 W. Durango Street

Phoenix, AZ  85009

Telephone (602) 506-8600

http://www.mcdot.maricopa.gov/technical/home.htm

SECTION 101	ABBREVIATIONS AND DEFINITIONS

101.2 Definitions and Terms

The following additions are made to definitions in Section 101.2 of the MAG Standard Specifications:

Contracting Agency:		Town of Queen Creek, Arizona

Consulting Engineer:	Kimley-Horn and Associates

Engineer:		Town of Queen Creek designee or Project Manager

Inspector:		Town of Queen Creek designee

Owner:			Town of Queen Creek, Arizona

SECTION 104	SCOPE OF WORK

104.1 Work to be Done

Section 104.1 of the MAG Standard Specifications is modified to add:

Town of Queen Creek Capital Improvement Project (CIP) No. A0306 Rittenhouse Road Improvements will widen a 2-mile stretch of roadway between the 213th Street alignment and Riggs Road from 2 lanes to 4 travel lanes with a center turn lane and adjacent bicycle lanes.  Improvements will tie-into both sides of the Maricopa County Department of Transportation (MCDOT) Queen Creek Wash Bridge project TT430 and then match the termination point of the newly constructed Riggs Road project TT538, just north of Alliance Lumber.

The Rittenhouse Road improvements and the Queen Creek Wash Bridge replacement will be completed at the same time, which includes the construction of two northbound and two southbound lanes and a modified center median.

Major elements of this project will include converting a portion of the existing 12kV overhead electric to underground, curb & gutter, sidewalk and driveway construction, storm drain and water system improvements, traffic signal, signage and pavement marking enhancements, as well as street lighting, irrigation and minimal landscaping improvements.

104.1.1 General

Section 104.1.1 of the MAG Standard Specifications is modified to add the following:

The work shall be as described in the specifications, as shown on the project plans, and in compliance with permit requirements.

The work shall conform to the Town of Queen Creek Design Standards and Procedures Manual, MAG Standard Specifications, latest edition, and other referenced specifications and special provisions.  Any section or sub-section of any Standard Specification included within these Contract Documents by reference only is understood to be made part of these Contract Documents. The CONTRACTOR shall have at least one copy of all referenced standard specifications and details at the job site at all times.

Standard Drawings and the manuals referenced in the project contract documents shall be required for construction of this project, insofar as applicable for any work to be performed within the public right-of-way and within the Town jurisdictional limits.

- Design and Construction Standards Manual for Water, Sewer and Irrigation Systems for Town of Queen Creek, dated 12/11/2013.

- Manual on Uniform Traffic Control Devices (MUTCD), 2009 Edition, with latest revisions.

All work mentioned or indicated within the Contract Documents shall be performed by the CONTRACTOR as part of this Contract unless it is specifically indicated in the Contract Documents that such construction is to be excluded or modified.

104.1.6 Pre-Construction Video

CONTRACTOR shall record and provide a copy of a pre-construction video along the project to the Town of Queen Creek prior to commencing work and retain a copy for their records. At a minimum, this video shall show the existing condition of the roads and surrounding features and improvements within the project limits, condition of landscaping and fences in close proximity of the work, and similar physical condition features.  The video shall be supplied to the Town on DVD disc in .wmv, flv, .mp4 or .mpg format.  There will be no separate payment for this video as it is considered incidental to the CONTRACTOR’S mobilization.

104.2 Alteration of Work

Section 104.2 of the MAG Standard Specifications is modified to add the following:

104.2.4.1 Re-use of Existing Materials by the Contractor

Where specifically called for in the approved plans, specifications or by the Town, certain existing materials may be re-used by the CONTRACTOR.   Otherwise, if the CONTRACTOR proposes to re-use existing materials, with or without either material repair, rejuvenation, processing, or blending with new materials to meet the required specification; or without CONTRACTOR’s verification of the available material quantity proposed for re-use from their own investigation or exploration, such proposal shall be deemed a Value Engineering Proposal (VEP) and shall be treated as such in accordance with Section 104.2.6 of these Special Provisions.  An affirmative answer to a bidder’s question regarding the possible re-use of any materials other than those specifically indicated as such within the construction documents shall be considered an answer that such a proposal will be considered by the Town if so submitted by bidder or CONTRACTOR with documentation of available quantities but is not an affirmative answer that such a proposal is approved and the bid can be based upon such proposal.

104.2.6 Value Engineering Proposals by the Contractor

Proposals may be submitted to the Engineer for modifying the plans, specifications, or other requirements of the contract for the sole purpose of reducing the total costs of construction without impairing in any manner the essential functions or characteristics of the project, including service life, economy of operations, ease of maintenance, benefits to traveling public, desired appearance or design and safety standards.

After execution of the contract, an initiative may be recommended by the Contractor. The initiative must be identified as a Value Engineering Proposal (VEP), and may include modifications to the plans or specifications, construction phasing procedures, or other contract requirements.

Any cost savings generated to the contract as a result of the VEP offered by the Contractor and approved by the Town will be shared equally between the Contractor and the Town.

Bid prices are not to be based on the anticipated approval of a VEP.  The unit bid price for all such work shall be deemed to be based on the engineered plans’ and specifications’ specified materials and labor including incidentals.  Such materials shall be considered to be furnished new, previously unused and as specified in accordance with the project specifications unless otherwise noted in the plans or specifications.  If a VEP is rejected, the contract work shall be completed in accordance with the original terms of the contract documents.  Substitutions based upon re-use of materials are not to be used for bidding purposes unless otherwise specifically stated as allowed by the Engineer or Town.  Any risk associated with bid prices based on an unapproved VEP contrary to these provisions is solely the bidder’s / CONTRACTOR’s risk.

Any decision whether to approve or accept a VEP shall be within the sole discretion of the Town. The Town will bear no liability for any delay in considering a VEP, the refusal to accept or approve such a proposal, or any other matter connected with a VEP.

SECTION 105 CONTROL OF WORK

Add the following:

105.2 Plans and Shop Drawings

Section 105.2 of the MAG Standard Specifications is modified to add:

All project materials and equipment not provided by Town of Queen Creek shall be approved by the Town or Engineer prior to purchase and installation.  Any work in which materials or equipment not previously approved by the Engineer are used shall be performed at the CONTRACTOR’S risk and may be considered as unauthorized and unacceptable and are not subject to the payment provisions of the contract.  Such materials or equipment may be subject to removal at the discretion of the Town.

Before ordering or installing any material or equipment, the CONTRACTOR shall submit two (2) printed copies or one electronic copy of each proposed material and/or equipment package, including shop drawings, manufacturer’s details or drawings, material and performance information and specification compliance to the Town for approval by the Town and / or Engineer.  To be acceptable, the submittal package shall be complete and contain all items supplied on the project by the CONTRACTOR, including pre-approved items.  The Town of Queen Creek reserves the right to reject an incomplete or unclear material submittal.  All items shall be identified by manufacturer's part number, model, specification or other pertinent catalogue information.  The materials from any catalog cuts shall be clearly indicated by the CONTRACTOR.  One (1) reviewed copy will be returned to the Contractor for further action.

All equipment or material specified or shown on signal plans, or other drawings, by brand name, part number, or model number is intended to be descriptive of the type, required features, and quality of material or equipment desired.  Another equal brand name, part number, or model number may be substituted so long as it is in accordance with these specifications and is equal in form, fit, function, performance, reliability, and is approved by the Engineer prior to utilization.

105.5 Cooperation of Contractor

The first paragraph shall be replaced with the following two paragraphs:

The CONTRACTOR shall be furnished with the approved plans and contract book containing the specifications and special provisions in an electronic publishing file format (.pdf).  The CONTRACTOR shall reproduce and furnish to their subcontractor(s) and crews the appropriate number of plan sets and contract books to allow successful execution of the project.  The CONTRACTOR and all subcontractors personnel shall have available on site at least one set of plans, referenced standard specifications and detail, and special provisions at all times when performing work.  This task is not a separate pay item and shall be considered incidental to the project work. The contractor and all subcontractors shall produce such documents when requested on-site by the Town inspector or project management staff.

The CONTRACTOR shall plan to conduct and attend weekly project progress update meetings throughout the duration of the project.  These meetings shall be held at the Town offices and a meeting room will be furnished free of charge.  The attendees shall include the CONTRACTOR’S Project Manager or Engineer, Project Superintendent, any Subcontractor’s representative whose attendance may be important and add to the discussion that is expected to occur at the meeting, the Town’s Project Manager, the Town’s Inspector, the Town’s Traffic Engineering representative, the Town’s Public Outreach representative, and other Town staff or consultants as may be desirable due to the expected content of the meeting.  The CONTRACTOR shall prepare and furnish an agenda and follow-up summary meeting notes reporting on the actions and discussion occurring at the meeting by agenda item.  The agenda shall include at a minimum discussion of schedule and upcoming three week look-ahead work forecast; traffic control issues and needs; specific upcoming work tasks that may need coordination or discussion; dust and erosion control measures performance and adequacy; specific issues that arose during the previous week that required discussion, action, and/or resolution; outstanding past issues; contractual issues that have arisen or are outstanding; utility coordination issues that may exist; and public outreach needs and updates.  Additional agenda items may be added or removed as the project and project progress dictates.  These meetings and related administrative efforts are not a separate pay item and shall be considered incidental to the project work. A format for such agendas and meeting notes can be furnished if desired and so requested.

105.5.1 Special Construction and Schedule Considerations

The CONTRACTOR is expected to perform certain portions of work at a time and in a manner that minimizes service interruption.  The CONTRACTOR shall work closely with the Town Utilities Department and Town Project Manager to develop a plan for work execution that minimizes service interruptions during operation hours, weekends or nights when the business are closed.  Work that interrupts electrical, sewer or water service shall be performed in a manner that allows the respective service to be restored as rapidly as possible and interrupts service for no longer than 8 hours.  A work plan shall be presented for concurrence to the Town Project Manager and affected Town staff at the CONTRACTOR’s earliest convenience but no later than at least seven (7) days prior to actual work efforts in area.  Adequate work planning to coordinate required operations, inspections, installation progress and completion testing shall be performed.

As such road closures, water service interruptions and other work will be an inconvenience to Rittenhouse businesses, their customers and suppliers, the CONTRACTOR shall work with the Town’s Public Outreach consultant, MakPro Services, to develop a construction/closure/service interruption pre-notice program for the CONTRACTOR to implement and follow.  CONTRACTOR is expected to utilize their knowledge and expertise to minimize the duration and extent of any partial closures, service interruptions, weekend and night work.  Alternative construction approaches for this work effort may be proposed by the CONTRACTOR for consideration by the Town and will be handled as Value Engineering Proposals.  Alternative construction approach and traffic control plan approval is at the sole discretion of the Town.

Adequate pre-warning and traffic control devices shall be used to clearly mark any partial roadway closures.  Adequate safety offsets, barriers and shoring shall be used to permit traffic to pass near the construction work areas.

The following additional paragraphs are added to Section 105.

105.6 Cooperation with Utilities

General: Conform to the requirements of MAG Section 105.6 except as modified to add herein:

The locations of existing underground utilities have been shown on the plans to the best of the Design Engineer’s knowledge.  However, it shall be the CONTRACTOR’s responsibility to field verify all utility locations and to coordinate in a timely manner with the pertinent utility companies so that any obstructing utility installation may be adjusted without delay to the CONTRACTOR’s project schedule. The CONTRACTOR shall be responsible for potholing all utility conflicts in a timely manner.  Delay claims due to utility relocation for which the CONTRACTOR failed to verify the location in a timely manner shall not be considered or approved.

The following utilities have facilities in the vicinity of the project limits.

Contacts for all utilities are listed on the plan cover sheet or within.

Coordination: Coordination with the pertinent utility companies has been a part of the development of this project. Construction activities shall be coordinated and scheduled to incorporate the following applicable utility construction activities.

- Century Link …

- Cox Communication …

- Queen Creek Irrigation District …

- Southwest Gas ….

- SRP …

ARIZONA 811: All utilities shall be blue staked by the CONTRACTOR prior to the start of construction.  If a utility is hit or discovered during construction activities, whether it is damaged or not, the CONTRACTOR or SUBCONTRACTOR shall immediately contact the Town Project Manager or Inspector or Arizona 811 Center and the utility company so the utility can be inspected.  Failure to notify all of the parties listed shall be cause for rejection of claims for delay or extra work by the CONTRACTOR or SUBCONTRACTOR.

Protection: CONTRACTOR shall endeavor to protect existing utility facilities present within the project limits but not anticipated to be in conflict with the improvements.  To this end, the CONTRACTOR is expected to contact the respective utility when performing work near their facility that could impact it to provide the utility the opportunity to be present and re-identify their facility location and to present suggestions regarding protection if they have a concern.  All such facilities shall be exposed or potholed if requested by the utility or town to verify clearance at no additional charge.

105.7 Cooperation between Contractors

General: Shall conform to the requirements of MAG Section 105.7 except as modified herein:

The CONTRACTOR is advised that there may be construction activity adjacent to the project site. The CONTRACTOR is to coordinate the work to accommodate the construction activities.

The CONTRACTOR shall contact the Town to verify all projects in the vicinity of this project.

The CONTRACTOR is advised that it shall schedule and coordinate all work activities so as not to adversely conflict with this work.

CenturyLink:

CONTRACTOR will be required to coordinate with CenturyLink during construction.  CenturyLink has existing underground and overhead facilities along the project.  CenturyLink will relocate the facilities that are in conflict with the improvements.

CenturyLink Contact:

Mr. Brett Beaty

(480) 768-4574

Email: Brett.Beaty@centurylink.com

Queen Creek Irrigation District (QCID) and Private Irrigation:

There are numerous existing QCID and private irrigation delivery systems and facilities located within the project limits and adjacent to the project limits.

Queen Creek Irrigation District Contact:

Mr. Burt Hatch, (480) 987-3002

Southwest Gas:

CONTRACTOR will be required to coordinate with Southwest Gas during construction.  Southwest Gas has existing facilities along the project.  Southwest Gas will relocate the facilities that are in conflict with the improvements.

Southwest Gas Contact:

Mr. Gene Florez

(480) 730-3841

Email:gene.florez@swgas.com

SRP Distribution:

CONTRACTOR will be required to coordinate with SRP Distribution during construction. SRP Distribution has existing overhead power lines within the project vicinity.

.

SRP Distribution Contact:

Mr. Vincent Silvestro, (602) 236-0432

Email: vincent.silvestro@srpnet.com

Town of Queen Creek Utility Department:

Town of Queen Creek utility Department Contact:

Mr. Darren Farar, PE

Utilities Engineering Manager

(480) 358-3476

Email: Darren.Farar@queencreek.org

105.8 Construction Stakes, Lines and Grades

Section 105.8, Construction Stakes, Lines and Grades is deleted and replaced by the following:

General: The CONTRACTOR shall furnish all materials, personnel, and equipment necessary to perform all surveying, staking, laying out of control lines and verifications of the accuracy of all existing control points which are delineated in the Contract Documents. The work shall be done under the direction of a Registered Land Surveyor licensed to practice in the State of Arizona.

Staking Outline: Prior to beginning any survey operations, the CONTRACTOR shall furnish to the Town of Queen Creek Project Manager, for approval, a written outline detailing the method of staking, interval of stakes, marking of stakes, grade control for various courses of materials, referencing, structure control, and any other procedures and controls necessary for survey completion. A part of this outline shall also be a schedule which will show the sequencing of the survey and layout work, throughout the course of the contract, listing a percentage of completion for each month.

Field Books: The CONTRACTOR shall furnish field books to be used for recording survey data and field notes.  These books shall be available for inspection by the Town at any time and shall become the property of the Town upon completion of the work.

Survey Control Verification:  The CONTRACTOR shall be responsible to stake construction elevations tied to the primary bench mark.

- Control Points (horizontal and vertical) – The existence and location of all survey monuments, bench marks and control points shall be verified prior to demolition or construction activity. Immediately notify the Town of Queen Creek Project Manager when location discrepancies greater than two-hundredths (0.02) foot horizontal or one-hundredth (0.01) foot vertical are found. All datum shall be Town of Queen Creek.  Control benchmarks may be disturbed by the construction performed.  The CONTRACTOR’s surveyor shall provide adequate temporary benchmarks to re-establish control benchmarks that are disturbed or destroyed.

- Control Lines – Construction control lines with grade breaks, transition points, horizontal and vertical curves, etc., shall be established and referenced prior to construction.

- Temporary Benchmarks – Temporary bench marks shall be established and referenced.

Pre-Construction Location Survey: All existing features which are located prior to construction shall be referenced to survey monuments along control lines by stationing in accordance with the construction documents and by offset distance from the control lines. All features shall be relocatable after construction. Distances measured shall be within one-hundredth (0.01) foot.

- Survey monuments – All survey monuments that lie within the construction area that may be disturbed shall be referenced to a specific point on at least four (4) stable objects by distance measurement. Reference objects shall be located no greater than three-hundred (300) feet from the survey monument being referenced.

- Water and Sewer line appurtenances – Water and sewer line surface appurtenances such as manholes, valves and cleanouts that lie within the construction area shall be located and noted on the Contractor’s approved construction documents prior to any demolition or excavation.

- Match Points and Removals – Verify the location (horizontal and vertical) of existing facilities to which the project connects. Immediately notify the Town of Queen Creek Project manager when location discrepancies of connecting facilities greater than one-tenth (0.10) foot horizontal or two-hundredths (0.02) foot vertical are found.

Construction Stakes: The Contractor shall set construction stakes and marks establishing lines and grades for road work, curbs, gutters, path, structures, buildings, centerlines for utilities and necessary appurtenances and other work as indicated in the Contract Documents and shall be responsible for their conformance with the plans and specifications.

The stakes shall be established in accordance with the following guidelines which represent the minimum standard and the CONTRACTOR shall provide additional stakes and controls necessary to perform the work.  The CONTRACTOR shall be held responsible for the preservation of all stakes and marks and will replace, at no additional cost to the Town; any construction stakes or marks which have been carelessly or willfully destroyed by acts of nature or other parties.

- Curbs, Curb and Gutter, Valley Gutter

- Curb and gutter shall be staked and installed prior to sidewalk, driveway and corner ramp construction.

- Cut/fill stakes for rough grade shall be set at one hundred (100) feet intervals with cuts to the top of curb.

- Finish grade stakes shall be set to curb grade at twenty-five (25) feet intervals, at grade brakes, angle points, transitions, returns, driveways, alley entrances, sidewalk ramps and other curb control points. The stakes shall be tacked for line on a 2-foot offset to the back of curb.

- Face of curb forms shall be checked for grade at flow line prior to placing concrete where longitudinal grades are two- tenth percent (0.20%) or less.

- Face of curb forms shall be checked for grade at gutter line prior to placing concrete for transitions at 30-foot intervals.

- Valley gutter stakes shall be set offset five (5) feet from the centerline of the valley gutter at twenty-five (25) feet intervals, marked with cuts to the flowline of the valley gutter.

- Storm Sewer and Drainage

All cuts will be to the invert of the pipe, given to the nearest one-hundredth (0.01) of a foot.

- Stakes for storm sewer will be driven flush with the existing ground, set on an offset at fifty (50) feet intervals.  Stakes will be marked with the offset and indicated cut.

- Wyes for laterals will be marked with a line only stake.

- Manholes shall be marked with the offset and indicated cut on top of manhole grade and inverts.

- Stakes for storm water inlets, tow (2) per inlet, will be set on a line normal to the roadway at the center line of the inlet five (5) and ten (10) feet from the face of curb.  The stakes will be marked with the offset to the face of curb and the cut or fill on the top of curb and inverts.

- Cut sheets shall be supplied to the Contractor and Town of Queen Creek Inspector.

- Roadway

Subgrade stakes shall be set to subgrade elevation at fifty (50) feet intervals on straight sections, twenty-five (25) feet intervals through vertical curves, on horizontal curves with radius of six-hundred (600) feet, or less, and/or slopes of less than four-tenths of one percent (0.4%) and the beginning and end of horizontal and vertical curves and grade breaks. Stakes shall be set at crown lines, at grade break lines and at edges of pavement which do not abut concrete curb and gutter or at the edge of pavement abutting vertical curbs or other structures whose surface grade will not be flush with the finished pavement grade. Quarter lines will be staked where the distance between the crown line stakes and the curb and gutter face exceeds twenty (20) feet. Select shall be staked the same as sub grade.

ABC stakes shall be set to ABC elevation at thirty-three (33) feet intervals on straight sections, twenty-five (25) feet intervals through vertical curves, on horizontal curves with radius of six-hundred (600) feet, or less, and/or slopes of less than four-tenths of one percent (0.4%) and the beginning and end of horizontal and vertical curves and grade breaks. Stakes shall be set at crown lines, at grade breaks and at edges of pavement which do not abut concrete curb and gutter or at the edge of pavement abutting vertical curbs or other structures whose surface grade will not be flush with the finished pavement grade. Quarter lines will be staked where the distance between the crown line stakes and the curb and gutter face exceeds twenty (20) feet.

Pavement edges shall be controlled by utilizing a wire control mechanism or screeding along a concrete gutter or other structure whose surface grade is flush with the finished pavement grade. Stakes shall be set to finished elevation at thirty-three (33) feet intervals on straight sections, twenty-five (25) feet intervals on curves with radius of six-hundred (600) feet, or less, and/or slopes of less than four-tenths of one percent (0.4%) and the beginning and end of horizontal and vertical curves and grade breaks.

- Sidewalks

Stakes are not required for sidewalks five (5) feet or less in width which are adjoining existing curb and gutter.

Sidewalk stakes shall be set to grade on an offset and tacked for line at twenty-five (25) feet intervals at the beginning and end of horizontal and vertical curves and grade breaks.  Where sidewalk grade and elevation differs from adjacent curb grade, sidewalk shall be staked at all grade breaks and elevation control points provided.

- Traffic Signing and Pavement Markings

The CONTRACTOR shall delineate the procedures and controls to be utilized in the Staking Outline.

- Landscaping

The CONTRACTOR shall delineate the procedures and controls to be utilized in the Staking Outline.

Re-establishment Survey:

Monument locations will be marked with "straddlers" (four nails with metal "shiners") driven into the pavement and placed in pairs, approximately six feet apart and opposite to each other. Lines connecting opposing pairs shall form a ninety-degree cross with three foot legs. The center of the cross will signify the exact location of the center of the monument to be set. Monuments will be drilled or punched after they have been set.

Manhole, valve box and cleanout locations shall be painted on the new pavement for rim adjustment.

Inspection and Acceptance of Work:

The Town reserves the right to make inspections and random checks of any portion of the staking and layout work.  Checks by the Town or his representative shall in no way relieve the Contractor of his/her responsibility to construct the project in accordance with the Contract requirements.  If, in the Town’s opinion, the work is not being performed in a manner that will assure proper control and accuracy of the work, the Town will order any or all of the staking and layout work redone at no additional cost.

Record Drawings (As-Builts):

A full-size set of project drawings shall be kept on-site and updated on a weekly basis or more frequent as necessary with a red pencil or red ink to reflect any field adjustments, changes, omissions, additions, etc. as they occur on the project. The Town Inspector will check site record drawings (as-builts) on a weekly basis to ensure all modified project elements have been properly recorded on the field plan set.  Record drawings reviews at progress meetings shall occur monthly.

The CONTRACTOR shall provide plan sheets for use in preparing final record drawings (as-builts). Information shall be shown on these plans in red opaque ink, depicting the constructed dimensions, elevations, grades and materials including locations of existing underground utilities found during construction.  Changed values shall be stricken out.

The CONTRACTOR shall exercise extreme care in handling any provided originals and will return them to the Town in like condition. In the event the originals are damaged or determined by the Town to be unacceptable, the CONTRACTOR shall replace the originals by contacting the Design Engineer of record and have new drawings produced. All costs incurred, as the result of replacing the originals shall be borne by the CONTRACTOR. The Town will be the sole judge in determining whether the record drawings (as-builts) are acceptable in either condition or detail.

All work included in the contract documents as well as changes to the contract shall be noted as correct or modified by either checking off the information if it is correct, or by drawing a neat line through the original data and writing in the correct information in opaque ink if the information is incorrect. Unless noted otherwise below in the minimum as-built requirement section, station/offset measurements will be from construction centerline/monument line both parallel and transverse to roadway; added items or location changes shall be physically drawn at revised or new locations on the record drawings (as-builts); and all measurements and stations should be to the nearest tenth foot.

The minimum requirements for record drawings (as-builts) acceptance is as follows:

  - Project Drawing Quantity Notations:

Any project drawing or quantity summary sheet that shows a quantity on it that is incorrect shall be corrected by drawing a neat line through the original quantity and writing in the correct information. When space on the drawing does not allow room to indicate the corrections, a separate table may be drawn on a separate sheet with reference on both plan sheets to the plan sheet that the table refers to or to the sheet where the table is located.

  - Existing/New Utilities:

All underground infrastructure utilities, whether depicted on the project plans or not, shall be verified, corrected or added to the record drawings (as-builts) noting the beginning and ending station/offset location and elevation of utility relative to finished roadway grade or other identifiable ground or permanent roadway/project feature. Any electrical installation work for street lighting or power connection shall be located relative to construction centerline/monument line or relative to back of curb and gutter (whichever is closer) including the depth of the facility.

  - Removals:

Dimensions and/or other volumetric descriptions and station/offset location of all removed items.

  - Curb/Gutter/Valley Gutter:

Beginning and ending station offset location of straight curb/gutter/valley gutter runs relative to construction centerline monument lone; flow line elevation; and station offset location of PC’s and PT’s.

  - Driveway/Alley Entrances:

Beginning and ending station/offset including driveway wings.

  - Sidewalk:

Beginning and ending station/offset and any other modification necessary to incorporate or avoid existing facility conflicts.

  - Sidewalk Ramp:

Curvilinear distance deviations measured along gutter flow line from curb and gutter PC/PT or other shifts/adjustments to properly align with pedestrian crosswalks or other modifications necessary to incorporate/avoid existing facility conflicts.

  - Path:

Beginning and ending station/offset and any other modification necessary to incorporate or avoid existing facility conflicts.

  - Median Island:

Beginning and ending station/offset of median and straight run median widths measured from back of curbs; beginning and ending station/offset of decorative median paving; bullnose radiuses; and measured widths of median in transition sections from back of curbs in 25 foot minimum increments or to bullnose radius PT/PC (whichever is less).

  - Roadway Pavement:

Beginning/ending station and measured completed roadway width from edge of pavement to edge of pavement in straight roadway sections; measured completed roadway width perpendicular to construction centerline/monument line from both edges of pavement to construction centerline/monument line in curved roadway sections; and actual sawcut removal/tie-in to existing pavement locations.

  - Pipelines:

When pipeline parallels the construction centerline/monument line, verify or correct the perpendicular distance between the two.  When pipeline angles relative to the construction centerline/monument line or is in a curved roadway section, as-built measured straight pipe run distances, angle points, changes in size, fitting/tee locations tied-in with practical known construction centerline/monument line location or other easily verifiable permanent point. Distances between fittings are from fitting centerline. Fire hydrant and catch basin branch lines are to be shown in profile including pipeline bends and collars.  All project drawing pipeline cross-sections and profiles are to be corrected to reflect modified pipeline locations/alignments.  Station and offset locations for sewer line laterals are from main line to ROW line with beginning/ending line location tied to a monument or to a property corner.  Locations where waterlines cross curb and gutter are to be noted by station.  Where waterlines run parallel to curb and gutter, note locations relative to back of curb or construction centerline/monument line (whichever is closer) including angle points and elevation.

  - Manhole/Catch Basin/Box Culvert/Valve/Cleanout/Tee:

Beginning/ending station and offset. Stationing is to commence at the downstream manhole/head wall (or as depicted on drawings) with location of tap/wye/tee/lateral/head wall locations clearly noted.

  - Bridges, Box Culverts and Other Structures:

Station/offset distances/centerline-bearing line/finished elevations of all bridge or structure elements.  Bridge deck and girder elevations must reflect before and after concrete placement elevations.  Inverts for all culvert barrel inlets and outlets and resulting culvert length(s) and slope(s).

  - Landscaping and Irrigation:

Note beginning and ending station offset elevation including size of PVC, sleeve pull-box/electrical-valve/water-service/tap/meter/bubbler/drip-line locations.

  - Traffic Signal:

Signal pole station/offset; electrical conduit, sleeve, controller, meter pedestal and pull box station/offset with distances of electrical conduit runs noted and tied in with known point.

  - Roadway Striping/Signage:

Any new/relocated sign shall be located by station and offset from construction centerline/monument line. Any change in roadway marking is to be noted on record drawings (as-builts).

  - Roadway Street Lighting:

Street light poles and pull boxes are to be located by station and offset from construction centerline / monument line.  Conduit location and depth of cover noted from top of curb.

  - Linear Items:

Fences, walls, ditches, etc. should be located by station/offset and tied in with a permanent point.

The record drawings (as-builts) shall be certified by an Arizona Registered Land Surveyor.  Record drawings (As-builts) shall be delivered to the Town Project Manager within thirty (30) calendar days from the date of final inspection and acceptance by the Town of the work substantially completed under this contract. Work under this bid item includes transfer of all information noted by the CONTRACTOR on the on-site record drawings (as-builts) set described above. Final payment will be made only after submitted record drawings (as-builts) are accepted by the Town (see “Measurement and Payment” below).

Measurement and Payment:

Construction Surveying and Record Drawings (As-Builts) will be measured as a single complete item of work together with construction surveying and paid at the Lump Sum price complete item of work as indicated on the Bid Schedule, which amount shall be considered full compensation for the work as described herein and required to clearly indicate all specific record drawings (as-builts) information.

Final payment for survey work under this bid item will be made when the Town accepts the final record drawings (as-builts). Should the CONTRACTOR fail to submit acceptable record drawings (as-builts) within the maximum 30 calendar day period noted above, the Town will execute a deduct change order for 10 percent of the bid item total from the contract (or $2,500.00, whichever is greater) for every five working day period that the CONTRACTOR fails to provide acceptable record drawings (as-builts) (not including Town review time). If the CONTRACTOR fails to submit acceptable record drawings (as-builts) after the 3rd submittal, the Town will deduct 50% from the bid item total from the contract (or $10,000.00, whichever is greater) and execute a final change order noting the Town’s justification for penalizing the CONTRACTOR for unacceptable record drawings (as-builts) preparation.

ITEM 105.xxxxx	construction survey, STAKING AND RECORD DRAWINGS	ls

SECTION 106 CONTROL OF MATERIALS

106.1 Source of Material and Quality

Section 106.1, add the following paragraph:

In order to expedite the inspection and testing of materials, the CONTRACTOR shall furnish complete shop drawings and submittals to the Town as to the origin, composition and manufacture of material to be used in the Work.  Such submittals shall be furnished promptly after execution of the Contract but, in all cases, prior to delivery of such materials.

106.2 Samples and Tests of Materials

- Section 106.2, add the following paragraphs:

The CONTRACTOR shall hire an independent third party Material Testing Firm to perform Quality Control testing for the project and pay all cost required.  The Material Testing Firm shall establish, provide and maintain an effective quality control program that details the methods and procedures that will be taken to assure that all materials and completed construction required by this Contract conform to Contract plans, technical specifications and other requirements, whether manufactured by  the Contractor, or procured from subcontractors or vendors.  Although guidelines are established and certain minimum requirements are specified herein and elsewhere in the Contract technical specifications, the CONTRACTOR shall assume full responsibility for accomplishing the stated purpose.

The CONTRACTOR shall maintain current quality control records of all inspections and tests performed.  These records shall include factual evidence that the required inspections or tests have been performed, including types and number of inspections or tests involved; results of inspections or tests; nature of defects, deviations, causes for rejections, etc; proposal remedial action and corrective actions taken if required.  These records must cover both conforming and defective features, and must include a statement that all supplies and materials incorporated in the work are in full compliance with the terms of the Contract.

Legible copies of all test results shall be furnished to the Town’s Project Manager in a Weekly Summary Report submitted in a timely manner to address any potential issues quickly.  Before final completion, the CONTRACTOR shall submit a final testing report summary containing all testing results which certifies that the work complies with the Contract Documents.  This testing report shall be sealed by a Professional Civil Engineer, registered in the state of Arizona who was responsible for overseeing the testing and sampling for said company.  There will be no separate pay item for this work; the cost should be incorporated into the applicable bid items’ unit prices.

The Town reserves the right to perform Quality Assurance testing required to certify the quality of materials for this project through its designated agent for professional materials testing services.  The purpose of assurance testing will be to verify the quality of the finished project for the Town.  The testing will, in no way, relieve the CONTRACTOR of his/her responsibility for his own quality control, assurance, and furnishing materials and finished products that meet the project specifications.  A pre-construction meeting to coordinate testing services shall be scheduled and held at the Town offices by the CONTRACTOR.

SECTION 107	LEGAL REGULATIONS AND RESPONSIBILITY TO PUBLIC

107.1 Compliance with Laws

Section 107.1 of the MAG Standard Specifications is modified to add the following:

The Town will endeavor to ensure that small, minority and woman-owned business enterprises shall have every opportunity to participate in providing professional services, purchased goods and contractual services to the Town without fear of discrimination based on race, religion, sex, age, disability or national origin.  A Small Business, Minority and Woman-Owned Business Enterprise goal has NOT been established for this contract. However, participation by such firms is encouraged.

The CONTRACTOR shall take all necessary measures to assure compliance by their employees and subcontractors with the adopted and applicable federal, state and local laws, ordinances, statutes, rules and regulations pertaining to stormwater discharge as well as air, groundwater and surface water quality.

107.2 Permits

Section 107.2 has been revised to read:

It is CONTRACTOR's responsibility to obtain all permits and licenses; pay all fees, charges, bonds and taxes; and prepare all required notices for the lawful execution of the work.  The Contractor is responsible for securing the Maricopa County Department of Transportation Right-of-Way Permits.  MCDOT permit fees will be reimbursed to the Contractor at cost with no markup from the Allowance for Extra Work Bid Item 109.21000 with submittal of a valid payment receipt.

107.2.1 Town Encroachment Permit

Town of Queen Creek permits for the improvements within the right-of-way are available from the Town at no cost to the Contractor and subcontractors for Town Capital Improvement Projects.  Please refer to the General Construction Notes on the plans for further information.  All permit requests must be filed by the Contractor or subcontractor performing the work, not the General or Prime Contractor.

A copy of all Town issued permits shall be provided to the Town’s Project Manager by the CONTRACTOR or SUBCONTRACTOR to whom issued.

107.2.2 Air Quality Permit

Air quality dust control (or earthmoving) permits may be obtained from Maricopa County Air Quality Department, Maricopa County Environmental Services, 1001 N. Central Avenue, Suite 125, Phoenix, Arizona 85004, Telephone Number (602) 506-6010. The following forms and actions related to air permits may be filed at Maricopa County’s self-service kiosks including Air Permit Cancellation Request, Contact Update Form, Subcontractor Change Request Form, Dust Control Plan Change, Dust Permit Cancellation Request, and Permit Acreage Increase Request. A kiosk is located at the Queen Creek Branch Library, 21802 S. Ellsworth Road, Queen Creek, AZ 85242.  Please visit the Air Quality kiosk location web page, https://www.maricopa.gov/1588/Kiosk-Locations for operating hours, maps and directions.

A copy of the earthmoving permit and dust control plan shall be submitted to the Town Project Manager prior to commencement of any earthmoving activities.  The required Dust Permit project site signs shall be posted near a project announcement sign at the project site.  The costs for such permits and signs shall be considered incidental to the work with no separate payments made.

107.2.3 AZPDES Construction Activity General Permit

The project is expected to require an Arizona Pollutant Discharge Elimination System (AZPDES) Construction Activities General Permit (CGP) based on the land area disturbed.  Unless otherwise directed by the Town, the CONTRACTOR shall be responsible for applying for and securing the Construction Activities General Permit (CGP) including preparation of the Stormwater Pollution Prevention Plan (SWPPP), filing of the NOI and NOT, maintaining the monitoring activities records, and performing all other related administrative, monitoring and recordkeeping activities.

107.2.3.1 Regulation Compliance

The CONTRACTOR shall be responsible for compliance with the AZPDES CGP requirements as administered by the Arizona Department of Environmental Quality (ADEQ).  This permit, administered by the Arizona Department of Environmental Quality (ADEQ), generally requires preparation of a Stormwater Pollution Prevention Plan (SWPPP), filing a Notice of Intent (NOI), monitoring possible pollution activities and event outcomes over the course of the construction activity, performing all administrative and record keeping duties related to the permit and SWPPP, and filing a Notice of Termination (NOT) following final project stabilization to close out the permit.  The CONTRACTOR shall take all necessary measures and perform all necessary actions to assure compliance by employees and subcontractors with the AZPDES CGP.  As the permittee, the CONTRACTOR is responsible for preparing, in a manner acceptable to ADEQ, all documents required by the regulations, which shall include but not necessarily be limited to, the documents noted previously above in this paragraph.

107.2.3.2 Stormwater Pollution Prevention Plan (SWPPP)

The CONTRACTOR shall author, develop, publish, implement, update and revise the SWPPP, as necessary, to assure compliance with permit requirements.  ADEQ has documents and check lists available on their web site to assist with preparation of a SWPPP.  http://www.azdeq.gov/node/524 and http://www.azdeq.gov/node/2328  The preparer should be aware that a complete SWPPP includes textual and graphic exhibit elements and includes measures and Best Management Practices (BMPs) for disturbance areas as well as equipment and materials parking, storage and service areas.  A copy of the SWPPP shall be retained on the project site at all times during construction.   Additional resources for preparing a SWPPP are available in the Drainage Design Manual for Maricopa County, Volume III Erosion Control.  This manual is available from the Flood Control District of Maricopa County, 2801 West Durango Street, Phoenix, Arizona 85009 or on-line at http://www.fcd.maricopa.gov/920/Directory-of-Documents.   The CONTRACTOR should consider the SWPPP a living plan and document.  Construction activity completion or new task initiation may require new or additional measures and BMPs be installed or used as construction progresses.

107.2.3.3 Notice of Intent (NOI) and Notice of Termination (NOT)

As of June 1, 2017, NOIs, NOTs and other CGP permitting forms are now completed, submitted and paid for completely on-line at ADEQ’s myDEQ on-line e-permitting portal. See this on-line page, http://www.azdeq.gov/node/1143 and this on-line page, http://static.azdeq.gov/mydeq/stormwater_get_new_noi.pdf for more information related to myDEQ.  This method requires the business user to register for an on-line account. Please visit the first link provided above for more information.  An electronic copy of the NOI shall be submitted to the Town Project Manager prior to commencing construction.  The CONTRACTOR should apply / submit for the NOI in a timely manner to prevent delays to project construction.  There are no known unique or impaired waters within the Town of Queen Creek for permitting purposes.

Upon project substantial completion, acceptance, final site stabilization and demobilization clean up, CONTRACTOR shall submit to the permitting agency a completed, duly executed Notice of Termination (NOT) for each NOI issued following the procedures in place at the myDEQ portal.  Such action will terminate all AZPDES CGP coverage for the project.

107.2.3.4 Time Extension or Claims Related to Permitting

Failure of the CONTRACTOR or a Subcontractor of any tier to submit a required NOI or other permit application or failure to properly administer or provide permit compliance action(s) that results in a construction delay or additional costs will not be granted a request or claim for time extension or additional cost.

107.2.3.5 Inspections

CONTRACTOR shall perform regular monitoring and inspections of all stormwater pollution control Best Management Practice (BMPs) on the project as required under the provisions of the AZPDES Construction General Permit for Arizona.  The CONTRACTOR shall prepare reports on such monitoring, inspection, corrective action and other activities as required by the CGP and shall retain the reports as noted in CGP and section below.  The CONTRACTOR shall maintain all stormwater pollution control BMP devices on the project in proper working order and replace those damaged beyond repair.  Such maintenance shall include necessary cleaning and/or repair for the duration of the project.  BMPs found to be inadequate shall be subject to corrective action to update the SWPPP and implement better suited and appropriate BMPs.  This provision includes adjusting the SWPPP, BMPs and actions related thereto to accommodate construction progress and new construction activities.

107.2.3.6 Recordkeeping

The CONTRACTOR shall retain the originals of all AZPDES CGP documents including the NOI, SWPPP, modifications and updates thereto, inspection and reporting forms and NOT for a period of at least three (3) years following the completion of the project and in accordance with the recordkeeping requirements of the CGP.  The CONTRACTOR shall make such documents available for inspection by representatives of the Environmental Protection Agency (EPA), ADEQ, Maricopa County Environmental Services Department or Flood Control District, and Town of Queen Creek upon request.

The CONTRACTOR shall post and maintain legible copies of all encroachment, right-of-way, dust control, air quality, storm water, electrical or other permits, NOIs and clearances at the site at all times.  The project superintendent or foreman having copies of all such documents within a notebook, electronic reading device, folder, binder or other document organization method when present on the site shall satisfy this requirement along with required posting by permitting agencies.  Electronic copies of all such permits and NOIs shall be provided by the CONTRACTOR to the Town’s project manager as such documents are secured and acquired.

107.2.3.7 Fines and Penalties

Any and all fines and/or penalties imposed by the ADEQ for CONTRACTOR’s failure to comply with any or all permit requirements and /or conditions or stipulations shall be borne solely by the CONTRACTOR and shall not be a basis of claim for additional payment due.

107.2.3.8 Payment

The lump sum price for the AZPDES CGP and any other permits noted above shall include all material, labor, and costs relating to the NOI, NOT, SWPPP, inspections, monitoring, corrective and other actions, applications, filings and payments therefore and associated therewith and thereto.   This includes, but is not limited to, preparation, installation, maintenance, removal, assuring proper operation, cleaning, replacing, and disposal costs associated with clean-up and repair following storm events, runoff or releases on the project.  The lump sum price for AZPDES and other permitting shall be inclusive of all related costs, and no additional claims shall be made by the CONTRACTOR under any other specification provision, including changed conditions.  CONTRACTOR shall be compensated for this bid item at a rate of 25% of the total bid price claimable with the first progress payment and the remaining 75% bid price claimable prorated over the remaining length on the project to substantial completion and clean up.

ITEM 107.xxxxx	 AZPDES and other permitting	LS

107.7 Barricades and Warning Signs

Section 107.7 of the MAG Standard Specifications is modified to add the following:

Project Information Construction Signs

It shall be the responsibility of the Contractor to furnish and erect project information construction sign(s) (Project Sign(s)) in accordance with this Specification.   The Project Sign(s) shall be professionally prepared and subject to approval by the Town.

The size, shape, and information to be depicted upon the Project Sign(s) are as described in the text and depicted in the template graphic presented below.  The Town will furnish the project name. The Town’s Public Outreach Consultant, MakPro Services, will acquire, secure, supply and furnish the project hotline telephone number and information website URL address.  The CONTRACTOR shall provide their business name and construction schedule information for use on the sign.  The Town shall furnish a native Adobe Illustrator (.ai) or encapsulated postscript (.eps) graphic file of the sign layout to the CONTRACTOR for use in ordering and manufacturing the sign(s).

The sign(s) shall be 4-feet by 8-feet in size. Sign panel materials shall be 3/4 inch, exterior grade plywood sign board or 0.080 inch aluminum sign blank. The sign(s) shall have three main parts. Part 1 shall have a CONSTRUCTION ORANGE background with BLACK letters and numerals. Part 2 shall have GRAY and BLACK backgrounds and progress indicators as depicted for the lower portion of the sign.  Part 3 shall have a black background with white letters. The sign(s) shall have ASTM Type XI grade retro-reflective sheeting applied over the entire sign including all lettering and graphics. Letter and logo height and spacing shall be as shown in the graphic file furnished.

The sign(s) consist of three parts and shall list the following information:

| Part 1 | 1. Project Name |
| --- | --- |
|  | 2. The word ”IMPROVEMENTS” |
|  | 3. Town Logo |
|  | 4. Project Construction Dates |
|  | 5. Contractor’s Business Name |
|  | 6. The Town’s Public Outreach Hotline telephone number AND project website URL address for project information. |
| Part 2 | 7. A Progress Bar section where colored, printed, vinyl coated magnetic sheet progress indicators with numbers can be placed over four default gray colored indicators during the project indicating progress milestones. |
| Part 3 | 8. The slogan “NEIGHBORS AT WORK. PLEASE DRIVE WITH CARE.” Or other slogan the Town determines to use. |

Construction Sign Detail (below)

The Progress Bar portion shall have rust resistant coated, flat steel bars mounted to the sign panel with rust resistant counter sunk screws or bolts, washers and nuts to which flexible, printed, die cut magnetic sheet progress arrow panels can be mounted during the duration of the project.

The progress arrow panels shall be colored, flexible, vinyl coated, die cut, 0.05 inch magnetic sheet, nominally 11” by 23.5” in size, on which progress value numbers are printed. Such coatings and printing inks shall be UV and weather resistant, die cut to size and shape of the indicators on the sign.  The progress arrow panels shall be provided with two color red backgrounds with white numbers and symbols.

Sign supports shall be 4 inch by 4 inch pressure treated wooden posts, painted WHITE and set a minimum of 2.5 feet into the ground. The sign(s) shall be mounted and installed so that the sign bottom edge shall be a minimum of 5 feet above the ground.  If an aluminum sign panel is used, the sign shall be mounted on two perforated tube, 1-3/4 inch square steel support stringers placed horizontally across the support posts and secured to the posts.  See ADOT Detail S-3, Sheet 4 of 4 for additional details and information. All hardware shall be rust resistant and meet ADOT standards.

The Project Signs shall be maintained in good condition by the Contractor for the duration of the project and shall be removed and disposed of by the Contractor during the final project clean up.

The required Project Signs shall be installed by the Contractor within fourteen days of issuance of the Notice to Proceed or an Authorization To Begin Limited Work.  The cost for the project sign(s) shall be considered incidental to the other project contract items.  No separate measurement or payment will be made for the project information construction sign(s).

The project will require three project information construction signs.  One sign will be erected at each end of the project along Crismon Road, just north of Queen Creek Road and south of Germann Road, facing what would be oncoming traffic, respectively.  The third sign shall be erected in the ROW along 220th Street just north of Queen Creek Road facing northbound traffic. The positioned and erected sign(s) shall not impair safe sight distance for the adjacent traffic, pedestrians and bicyclists nor impede drainage flow.  The signs are expected to be posted within the adjacent right-of-way or, with permission of the land owner, on adjacent property.

107.12 Furnishing Right-of-Way

Section 107.12 of the MAG Standard Specifications is modified to add the following:

Before utilizing any TCE provided on property outside of the project right-of-way or easement(s), the Contractor shall provide written notice of intent to utilize the TCE to the residents living or business operating on the property a minimum of 48 hours in advance.  This notice shall include a brief “work to be performed” description and the expected work duration.  This notice shall also include a Contractor’s staff contact name and phone number for the convenience of the residents, in case of emergency or complaints.  This requirement is in addition to any public outreach efforts utilized or performed by the Town.  Names dates and times of who the notice was provided to shall be recorded and provided to the Town project manager.

Section 108 Commencement, Prosecution and Progress

108.1 Notice to Proceed

Section 108.1 of the MAG Standard Specification is modified to add the following:

The Town shall issue a notice to proceed (NTP) for the improvements related to Projects A0306 and TT430 to the CONTRACTOR once all contractual documents are obtained and appropriately executed.  Utilities with facilities located in the project vicinity, particularly SRP and QCID are aware of the project schedule and are expected to have their relocation work completed prior to the anticipated start of the project.  The CONTRACTOR may be provided with a letter approving the authorization to perform limited work that will benefit the project completion schedule and Contractor’s progress if any utilities fail to complete their facility relocation prior to the anticipated start of the project.  This may also occur if other construction by others within the project limits is not completed and conflicts with the CONTRACTOR’S proposed work schedule.

108.4 Contractor’s Construction Schedule

Add the following paragraphs at the end of the section:

The CONTRACTOR shall plan to begin work as early as possible.  All project work shall be substantially complete within 180 days of the Notice to Proceed and Final Completion shall occur a year later.

The CONTRACTOR shall submit an overall project schedule at the commencement of the project as noted above.  This schedule shall be maintained and updated bi-weekly throughout the project to reflect significant schedule changes appropriate to the allowed project duration.

The CONTRACTOR shall coordinate these update needs with the contracting agency representative.  The schedule shall be presented to the Agency in both electronic publishing (.pdf) and hard copy format.  The Town may request electronic format submittal of the schedule and updates to software directly by the CONTRACTOR.

During the execution of the project, The CONTRACTOR shall also submit a three week look-ahead forecast schedule updated weekly.  These schedules shall be presented as a subset of the overall schedule or in a format such as an Excel spreadsheet and shall depict the upcoming work tasks and associated durations by days.  Special actions or tasks for certain subsets of the work may be requested to be presented separately by the Agency and shall be furnished if so requested.  The look-ahead schedule intent is to identify upcoming traffic control and public outreach needs, monitor anticipated progress and upcoming tasks, and allow the project team to discuss and coordinate project needs.  These look-ahead forecast schedules shall be presented to the Agency in both electronic publishing (.pdf) and hardcopy format.

Furnishing project schedules and updates to same is not a separate pay item and shall be considered incidental to the project work.

The CONTRACTOR shall review and assess all materials availability and delivery timeframes very early in the project and plan their activities for shop submittals, ordering and construction means and methods accordingly.  If the CONTRACTOR discovers or encounters any potential schedule issues in this assessment process that will materially impact, restrict or prohibit work commencement and completion in accordance with the proposed contract dates noted above, they shall promptly notify the Town Project Manager to discuss the issues and develop a mutually acceptable course of action.

108.5 Limitations of Operations

Add the following provisions:

108.5.1 Fugitive Dust Control Operations and Pollution Prevention Management Plan

The CONTRACTOR shall create, develop, publish and have a plan in place to control fugitive dust and track off soils.  The plan shall indicate what best management practices (BMPs), measures, actions and procedures are to be implemented and executed by the CONTRACTOR to accomplish the pollution prevention (including fugitive dust control) goals.  The CONTRACTOR shall apply for, pay for and secure the required permits for the project as appropriate.  All required permit signage shall be created and erected as required by law, promulgated regulations, project specifications, special provisions, plan notes and permit requirements.  If performing work extended under an approved and issued general or blanket-type permit, all permit requirements issued in conjunction with the permit shall be met.

108.5.1.1 Mechanical Sweeping

Mechanical sweeping shall be included as a part of the project’s fugitive dust control and Stormwater Pollution Prevention or Management Plan to control track out of earthen and other materials from the project site.  The limits of sweeping shall include all adjacent, pass-through and nearby paved street areas where construction related vehicles and/or vehicles hauling and/or delivering materials to or from the project site for a minimum distance of ¼ mile or further as field observations indicate are necessary.  Sweeping operations frequency and duration shall be as necessary to remove any such debris or materials that have been tracked out of the project site.  When such sweeping operations extend across railroad tracks, the mechanical sweeping equipment shall be raised prior to and when crossing the tracks to prevent damage to the rails or crossing surface and to prevent false signals from being generated due to low voltage electrical short circuiting.

108.5.1.2 Watering

Watering operations shall be included as a part of the project’s fugitive dust control and Stormwater Pollution Prevention or Management Plan to control track out of earthen and other materials from the project site.  Watering operations shall take place on all earthen surfaces within the project limits subject to vehicular or construction equipment traffic or surfaces or friable materials that have been or are being disturbed by construction operations.  Water shall be applied by means of, but not limited to, tanks, sprayers, pipes, hoses, nozzles or sprinklers.  The limits of watering may extend to and include adjacent, pass-through and nearby paved street areas where construction related vehicles and/or vehicles hauling and/or delivering materials to or from the project site as field observations indicate are necessary to remove and control fugitive dust and material track out.  Watering operations frequency and duration shall be as necessary to minimize or prevent creation of fugitive dust from the construction activities on the project site and to facilitate removal of significant debris or materials that may have been tracked out of the project site.  When such watering operations extend across railroad tracks, the watering equipment and operations shall be placed and performed in such a manner as to not damage the railroad tracks and railroad subgrade; and to prevent damage to the rails, ties or crossing surface; and to prevent false signals from being generated due to low voltage electrical short circuiting.

All such dust control work and related efforts shall be considered incidental and part of the overall work with no separate payment made for such efforts.

SECTION 109	MEASUREMENTS AND PAYMENTS

Add the following subsections to the MAG Standard Specifications:

109.5.6 Bonds and Insurance

Add the following paragraph:

When additional work is being paid for under an allowance item included in the original bid schedule and contract, no additional compensation shall be paid to the CONTRACTOR for cost of insurance or performance and payment bonds as such cost is already included in the original contract price.

109.10.1 Mobilization

The Town will compensate CONTRACTOR for one-time, round trip mobilization/demobilization  of  CONTRACTOR’s  personnel,  equipment,  supplies  and  incidentals, establishment of offices, buildings and other facilities required for the performance of the work on the project, as well as preparatory work and operations prior to the commencement of the work on the project site.

109.10.2 Measurement

Measurement of all work completed under the contract will be measured by the Town according to United States standard measures.  The methods of measurement and computation to be used in determination of quantities of materials furnished and of work performed under the contract will be those methods generally recognized as conforming to good engineering practice.  Mobilization/demobilization will be measured for payment by the lump sum as a single complete unit of work.

Measurement for Traffic Control shall be made on an Allowance basis.  This item shall include all material, equipment and labor necessary to facilitate traffic control per the contract documents.

109.10.3 Payment

Payment for pay items in the proposal will be as indicated in the applicable standard specification or in the special provisions.

Payment for mobilization/demobilization, measured as provided above, will be made at the contract lump sum price.   Payment shall be made in equal one-third portions.   The first payment will be paid with CONTRACTOR’s initial billing.  The second payment will be made when the total payments to CONTRACTOR for the bid items, exclusive of payments for mobilization/demobilization, equals one-half of the total bid by CONTRACTOR, exclusive of mobilization/demobilization.  The remaining one-third will be paid as part of the second to last progress payment.  Final payment due CONTRACTOR will be for retention.

When other contract items are adjusted as provided in Section 109, and if the costs applicable to such items of work include mobilization costs, such mobilization costs will be considered as recovered by CONTRACTOR in the lump sum price paid for mobilization, and will be excluded from consideration in determining compensation under Section 109.

If the CONTRACTOR performs a second mobilization/demobilization of personnel, material and/or equipment at the Town Project Manager’s express written request, the Town will compensate the CONTRACTOR for such expenses at the CONTRACTOR’s actual costs.   The CONTRACTOR shall provide all documentation for these costs at the request of the Town Project Manager.

ITEM 109.xxxxx	 MOBILIZATION/Demobilization	LS

An Allowance for Extra Work bid item is included in the bid schedule for unforeseen items discovered during the course of construction or directed work determined desired by the Town and adjacent to or within the project limits or work zone.  Extra work involving unit bid items already included in the Bid Schedule shall be paid for at such unit rates.  Work items not provided in the Bid Schedule shall be negotiated with the Contractor to determine total prices for extra work.  Only actual extra work items may be invoiced against this bid item per MAG 109.4 and 109.5.

ITEM 109.xxxxx	 allowance for extra work-CIP	al

Payment for Traffic Control and Uniformed Off-duty Law Enforcement Officers shall be made at full reimbursement of actual invoices with a maximum 5% markup.  Allowances for Traffic Control and Off-Duty Officers provided in the bid schedule shall be invoiced against only charges for such items with supporting invoices provided with the payment request.

ITEM 109.xxxxx	ALLOWANCE FOR Traffic Control	AL

Item 109.xxxxx	ALLOWANCE FOR Off-Duty Officer	AL

PART 200 - EARTHWORK

SECTION 201 CLEARING AND GRUBBING

201.1 Description

Section 201.1 of the MAG Standard Specifications is modified to add the following:

Trees that are to be removed shall be completely unearthed, including the root structure.  The resultant void shall be filled with soil and compacted to required levels based on the location within the project.

201.5 Payment, Clearing and Grubbing

Section 201.5 of the MAG Standard Specifications is modified to add the following:

Payment for clearing and grubbing will be made at the contract lump sum price, and shall constitute full compensation for furnishing all material, labor, tools and equipment and accomplishing all work associated with clearing and grubbing as described in this specification, the special provisions and on the construction plans.

ITEM 201.xxxxx	clearing & Grubbing	LS

SECTION 205	ROADWAY EXCAVATION - DRAINAGE

205.1 Description

Is revised to read:

Roadway Excavation - Drainage shall consist of excavating, grading, hauling, placing and compacting all types of materials encountered in the constructing of the temporary retention basins, excavating for the scupper spillways, and under-cutting for installation of dumped riprap and other drainage-related area designated on the plans or specified in the Special Provisions after placement and compaction of excavated material in cuts or embankments in the roadway prism as subgrade preparation along the project. Work shall consist of excavating to the specified lines, grades and compaction.

205.7 Measurement

Is revised to read:

Roadway Excavation - Drainage will be measured by the cubic yard in the original space occupied and the volume of the material removed will be computed by the average end area method.

205.8 Payment

Is revised to read:

Roadway Excavation - Drainage for basins and other drainage features will be paid for at the contract unit price per cubic yard.  The cost shall include excavating, sloping, rounding tops and ends of excavations, loading, depositing, conditioning, spreading, and compacting the material complete in place and disposal of surplus material.

ITEM 205.xxxxx	ROADWAY EXCAVATION - DRAINAGE	CY

SECTION 215 EARTHWORK

215.1 Description

Add the following to this section:

The work in this section consists of excavation, fill and grading and disposal of excavated and removed material for the construction of the retention basins and channels as shown on the plans.  Any excavated material not used for the project is to become the property of the Contractor and removed for the site.

215.3 Excavation

Add the following to this section:

The basins and channels shall be excavated to the neat lines shown in the plans.  Basin bottom dimensions and locations and basin side slopes are included in the plans.  All channel surfaces and basin side slope surfaces shall be compacted to a uniform density of not less than 95%.  Finished channel and basin surfaces shall be graded to drain.

215.5 Grading

Replace this section with the following:

Grading of the basins embankments, access roads and channels shall conform to the following tolerances:

- A vertical tolerance of none above and three (3) inches below the specified grade will be allowed on:

- Basin side slopes in both cut and fill;

- Embankments and access road side slopes in cut;

- Channels in both cut and fill;

- Top surface of access road in both cut and fill;

- Embankments and access road side slopes in fill;

- Top surface of embankments in both cut and fill; and

- All landscaped areas.

- A vertical tolerance of plus or minus 0.1 foot from the specified grade will be allowed on:

- The basin bottom; and

- The channel invert

215.7 Measurement

Add the following to this section:

Grading and subgrade excavation required for riprap placement will be considered incidental to those items.  Excavation and grading of roadside channels shall be included in the measurement of Roadway Excavation, Section 205.

215.8 Payment

Add the following to this section:

Earthwork for retention basins will be paid for the contract unit price per cubic yard of excavation.  Such price shall include all labor, equipment and materials for stripping, excavation, fill, backfill, compaction and grading, dust control, survey as required, hauling, removal and disposal of excavated material and debris.  Excavation and grading of roadside channels shall be included in the payment of Roadway Excavation, Section 205.

SECTION 220	RIPRAP CONSTRUCTION

220.1 Description

This section is modified to add:

Loose Riprap over non-woven, geosynthetic filter fabric is to be placed at all scupper spillway terminations at temporary retention basins.  Riprap is to be installed at the bottom of the spillway, up and across the opposite basin side slope to the high water elevation; width of riprap area to match scupper spillway width as shown in the plans.

220.2 Materials

Riprap aggregate shall be stone and cobbles angular and irregular in shape and be of similar color to adjacent landscape aggregate (decomposed granite, gravel mulch or blanket as described) unless otherwise noted in the plans.  Rounded, river run materials may be furnished if they have been crushed and processed to produce angular, irregular shaped, unrounded particles meeting the specified particle size distribution / gradation to the satisfaction of the Town’s project representative. Samples of the proposed processed materials shall be furnished for review or the CONTRACTOR shall arrange a visit to the aggregate supplier’s processing facility and proposed processed material stockpile by the CONTRACTOR and the Town’s project representative to view and approve the proposed material prior to use.  If the material proposed is rejected by the Town for any reason, the CONTRACTOR shall locate an alternative source of material meeting the requirements and acceptable to the Town at no additional cost to the Town.

Erosion Control Geosynthetic: Erosion control geosynthetic shall meet the requirements of MAG Specification Section 796 and Table 796-3 Class B.

The identification, packaging, handling, and storage of the geotextile fabric shall be in accordance with ASTM D 4873.  Fabric rolls shall be furnished with suitable wrapping for protection against moisture and extended ultraviolet exposure prior to placement.  Each roll shall be labeled or tagged to provide product identification sufficient to determine the product type, manufacturer, quantity, lot number, roll number, date of manufacture, shipping date, and the project number and name to which it is assigned.  Rolls will be stored on site or at another identified storage location in a manner which protects them from the elements.  If stored outdoors, they shall be elevated and protected with a waterproof, light colored, opaque cover.  At no time shall the fabric be exposed to sunlight for a period exceeding 14 days.  Fabric shall be placed in the manner and at the locations shown on the project plans.  The surface to receive the fabric shall be free of obstructions, depressions, and debris.  The fabric shall be loosely laid and not placed in a stretched condition.  The fabric strips shall be placed to provide a minimum 24-inch of overlap for each joint.  On horizontal joints, the uphill strip shall overlap the downhill strip.  On vertical joints, the upstream joint shall overlap the downstream strip.

220.5 Riprap Placement

Add the following:

The top of rock riprap shall not extend above the finish grades shown on the plans or the existing adjacent grades.  Over excavation shall be provided matching the full riprap thickness called for on the plans prior to placement of riprap.

220.8 Payment

Section 220.8 of the MAG Standard Specifications is modified to add the following:

Payment for geosynthetic fabric will be made at the contract unit price per square yard and the payment for riprap will be made at the contract unit price per cubic feet.  Payment shall be full compensation for furnishing all labor, materials, tools, and equipment, and doing all the work involved in fabricating and placing the riprap.  This includes, but is not limited to, transport, processing, and placement of the riprap and underlayment fabric, respectively, as described in the MAG Standard Specifications, on the plans, and in the special provisions.

item 220.xxxxx	Geosynthetic Filter FabRic (Erosion Control)	SY

item 220.xxxxx	Riprap construction, 12” thick, d50=6”	cy

PART 300 – STREETS AND RELATED WORK

SECTION 301 SUBGRADE PREPARATION

301.1 Description

Section 301.1 of the MAG Standard Specifications is modified to add the following:

This work will include all pavement removal, excavation, embankment, placing, hauling, conditioning, compacting, subgrade preparation and all hauling and placing of import or disposing of excess material.  Excavation and embankment related work performed under this provision shall comply with MAG Specification Sections 205, 206, 211 and 215 (Subgrade Preparation) and 601.

301.2 Preparation of Subgrade

Section 301.2 of the MAG Standard Specifications is modified to add the following:

Subgrade preparation shall include all required excavation, embankment, and other grading detailed or implied by the plans and specifications within and outside the roadway prism, except as noted herein to be paid for separately.

Contractor shall include the cost of roadway earthwork as part of the subgrade preparation for construction of the street, excluding drainage excavation.  This work includes all grading which is required to obtain the proper subgrade and finished elevations of the roadway and other areas depicted on the plans except as noted. The grading work will extend beyond the centerline or back of curb as necessary to construct the complete street cross-section and to provide finished grades along the roadway prism as shown on the plans.  Note this work does not include and is separate from the drainage earthwork pay item pertaining to the drainage basins and other drainage excavation as noted in Section 205.

Excess earth material shall become the property of the CONTRACTOR and disposed of properly in a legal manner off-site or may be stock piled at a designated site on Town owned property.

Relative compaction requirements for subgrade preparation are defined by MAG Specifications Section 301.3.  Compaction requirements for structure excavation are defined by MAG Specification 206.  Subgrade preparation and compaction shall be as follows:

- Exposed native soils that will receive fill, pavement areas, and exterior slabs including sidewalks, once properly cleared, should be prepared in accordance with the project geotechnical report.  In absence of such report or guidance therein, such soils shall be scarified to a minimum depth of six inches, conditioned, to near optimum moisture content, and compacted to 95 percent of the maximum dry density as determined by the applicable ASTM test methods.

Required Inspections

Roadway subgrade shall be inspected during grading operations and prior to placing aggregate base course. The minimum number of density tests required is one for each 1000 square yards, or as otherwise recommended or required by these specifications or the geotechnical report.

301.7 Measurement

Section 301.7 of the MAG Standard Specifications is modified to add the following:

Subgrade Preparation will be measured by the square yard of area of new asphalt concrete pavement and chip seal pavement per budgeted project.

Prior to bidding the work, the CONTRACTOR shall thoroughly satisfy himself as to the actual conditions and earthwork quantities involved.  No claim shall be made for any earthwork excess or deficiency thereof after the beginning of grading unless soil conditions require additional processing to attain subgrade sufficiency.

301.8 Payment

Section 301.8 of the MAG Standard Specifications is modified to add the following:

Payment for roadway excavation and fill is included in the subgrade preparation item and shall include excavating, hauling, sloping, rounding tops and ends of excavation, loading, depositing, conditioning, spreading, and compacting the material complete in-place and includes any import of material and as required disposal of surplus material.

Payment for subgrade preparation will be made at the contract unit price per square yard based on the pavement areas defined above.  Such payment shall constitute full compensation for all of the work required to prepare the subgrade

item 301.xxxxx	subgrade preparation	SY

SECTION 310	PLACEMENT AND CONSTRUCTION OF AGGREGATE BASE COURSE

310.3 Compaction

Add the following:

Base material shall be placed in accordance to Section 310 of the Standard Specifications.  Compaction of existing base shall be accomplished by scarifying the full depth of the base course.  The scarified and compacted base shall be true, even and uniform conforming to the grade as shown in the project plans.

310.4 Payment

Section 310.4 of the MAG Standard Specifications is modified as follows:

Payment for untreated base (ABC) will be made at the unit bid price per square yard. Such payment shall constitute full compensation for supplying, placing and compacting the ABC complete in place, with no allowance for waste, and shall include labor, equipment, tools and incidentals necessary to complete the work as defined on the project plans and in the specifications.

Item 310.xxxxx	Aggregate Base Course - 12" Thick	SY

SECTION 321	PLACEMENT AND CONSTRUCTION OF ASPHALT CONCRETE PAVEMENT

321.1 Description

Section 321.2 of the MAG Standard Specifications is modified to add the following:

Inspection and Acceptance:

The Town of Queen Creek will perform inspection and will require twenty-four (24) hour notice. The Contractor shall have an independent testing company on-site at the on-set of construction to establish a rolling pattern and monitor compaction. A minimum of one density test for every 1000 square yards is required.

Certificates of mix design for each product is required prior to paving.

321.5 Mix Design

Add the following:

The A-1/2” Mix Designation AC Course and A-3/4” Mix Designation AC Course mixtures shall meet the East Valley Asphalt Committee (EVAC) requirements for Marshall or Gyratory Mix design with the exception that the binder shall be polymer modified as required in Section 711.  Refer to the “report on Geotechnical Investigation” dated November 22, 2016, prepared by Speedie and Associates for this project for pavement recommendations.

321.13 Payment

Section 321.9 of the MAG Standard Specifications is modified to add the following:

Payment for AC Pavement will be full compensation for placing all materials specified, with no allowance for waste, and shall include labor, equipment, tools, and incidentals necessary to complete the work complete in place in accordance with the construction plans and as prescribed and directed by the Town of Queen Creek. Payment will be made at the contract bid price per square yard.

item 321.xxxxx	Asphalt Concrete Pavement – A 1/2” Mix 1.5” Thick	SY

Item 321.xxxxx	Asphalt Concrete Pavement – A 1/2” Mix 2” Thick	SY

Item 321.xxxxx	Asphalt concrete pavement – A 3/4” mix 2.5” Thick	SY

item 321.xxxxx	Asphalt concrete pavement – a 3/4” mix 3” thick	sy

item 321.xxxxx	Asphalt concrete pavement – thickened edge	lf

item 321.xxxxx	Asphalt concrete pavement – safety edge	lf

SECTION 329	TACK COAT

329.3 Application

Section 329.3 of the MAG Standard Specifications is modified as follows:

Tack coat shall be diluted in the proportion of 50 percent water and 50 percent emulsion and applied at the rate of 0.08 gallons per square yard.  Application shall be made in advance of subsequent construction as ordered by the Engineer.

329.7 Payment

Section 329.73 of the MAG Standard Specifications is modified as follows:

Payment for the application of tack coat will be made at the unit bid price per ton.  Such payment shall be compensation in full for supplying and applying the tack coat complete in place in accordance with the specifications and the project plans.

iTEM 329.xxxxx	Tack Coat	TN

SECTION 336	PAVEMENT MATCHING AND SURFACING REPLACEMENT

336.1 Description

Section 336.1 of the MAG Standard Specifications is modified to add the following:

This section controls the work associated with sawcutting pavement, as required by the construction plans.

336.2.4.1 Permanent Pavement Replacement

Add the following:

Permanent pavement replacement is not required at locations where new full pavement construction is called for on the roadway plans.  Surface replacement and matching will only be required at locations where existing asphaltic pavement is being removed for trenching to install or remove existing utilities or irrigation facilities; and at new pavement matching to existing pavement at continuation for new roadways as shown on the approved roadway construction plans and details.

336.5 Payment

Section 336.5 of the MAG Standard Specifications is modified as follows:

Payment for sawcutting pavement will be made at the unit bid price per linear foot. Such payment shall constitute full compensation for providing equipment and accomplishing this work complete in place as identified on the construction plans and in the specifications.

item 336.xxxxx	pavement Matching and Surfacing Replacement	SY

MAG Std. Det. 200, Type C

ITEM 336.xxxxx	sawcut asphaltic concrete pavement	LF

SECTION 340 CONCRETE CURB, GUTTER, SIDEWALK, SIDEWALK RAMPS, AND DRIVEWAY

340.1 Description

The work under this item includes new concrete construction. This work shall conform to the requirements of the MAG Uniform Standard Specifications for Public Works Construction.

Where new traffic signal pole push buttons are to be installed adjacent to existing sidewalks or curb ramps, the Contractor shall construct a new ADA accessible apron or provide access around the pole base as shown in the details on the plans. The Contractor shall modify these details as necessary to accommodate any changed field conditions or variation in pole location at no additional cost to the Town.

When constructing the signal pole apron, the Contractor can either block out the pole base or cast the anchor bolts into the apron. Regardless of the method chosen, the Contractor shall grout the base following installation and leveling of the pole in accordance with the Standard Specifications. The Traffic Engineer will decide on the better of the two options available on site according to placement.  All pole foundations shall be flush with apron or sidewalk.

Prior to pouring any concrete the Contractor shall contact the Town of Queen Creek Traffic Engineering Department 48 hours in advance for an inspection.

340.3 Construction Methods

Section 340.3 of the MAG Standard Specifications is modified to add the following:

Construct in accordance with Sections 340, 601 and 725, except as modified below.

Sub-grade shall be compacted to 95% at a moisture content of optimum or up to 2% below. Compaction tests shall be done for every 300 feet of curb, or once per pour day minimum.

There shall be a maximum interval of 50 feet between expansion joints in the curb and gutter.

Each concrete load shall be tested for air, temperature, and compressive strength.

340.5 Measurement

Section 340.5 of the MAG Standard Specifications is modified to add the following:

The detectable truncated domes shall be the Neenah R-4984 cast iron, 24” x 30” plates unpainted/uncoated.  Detectable warnings shall not be measured for payment, this item is considered integral to the walking surface that they form a part of and the cost is included in the related pay item.

340.9 Payment

Section 340.9 of the MAG Standard Specifications is modified to add the following:

Unless otherwise quantified on the plans, no additional measurement and payment will be made for additional materials and labor needed to match existing grades to proposed driveways, such cost shall be included in bid items for which the work is necessary.

Payment will be full compensation for placing all materials specified complete in place, with no allowance for waste, and shall include labor, equipment, tools, and incidentals necessary to complete the work as prescribed and directed by the Town.

Payment for sidewalk ramp per City of Chandler Detail C-258 will be made at the contract unit price per each for a dual ramp installation.  Ramp detail C-258 includes both a single ramp and a dual ramp detail; a ramp detail as shown on the Project construction plans has been modified for future installation to a dual ramp condition, and will be paid as a dual ramp.  Such payment shall constitute full compensation for performing all of the work associated with the construction ramps as defined on the project plans, details and in the specifications.

ITEM 340.xxxxx	Concrete Curb & Gutter, MAG Std. Det. 220-1, Type A H=6”	LF

item 340.xxxxx	Concrete Curb & Gutter, MAG Std. Det. 220-1, Type A H=6”	LF

w/Depressed lip

item 340.xxxxx	Concrete Mountable Curb & Gutter, MAG Std.	LF

Det. 220-2, Type F

item 340.xxxxx	Concrete Curb Transition, MAG Std. Det. 220-2, Type F	LF

to Type A

item 340.xxxxx	Concrete Sidewalk Ramp w/Detectable Warning	EA

Per City of Chandler Det. C-258

ITEM 340.xxxxx	Concrete Sidewalk, 6' Wide, MAG Std. Det. 230	SF

ITEM 340.xxxxx	Modify back of existing ramp for access to push 	LS

Button per ToQC det. TS-05

SECTION 345	ADJUSTING FRAMES, COVERS, VALVE BOXES AND WATER METER BOXES

345.6 Payment

Section 345.6 of the MAG Standard Specifications is modified to add the following:

Payment for manhole, water or gas valve frame and cover; and pull box grade adjustments will be made at the contract unit price per each. Such payment shall constitute full compensation for performing all of the work associated with the manhole grade adjustments as defined on the project plans and in the specifications.  Adjustment rings for polymer manholes shall be polymer.

item 345.xxxxx	Adjust pull box to grade	ea

item 345.xxxxx	Adjust V.B., Frame and Covers, MAG Std. Det. 391-1, type A	ea

item 345.xxxxx	Adjust Manhole, Frame & Cover, MAG Std. Det. 422	EA

SECTION 350	REMOVAL OF EXISTING IMPROVEMENTS

350.1 Description

Section 350.1 of the MAG Standard Specifications is modified to add the following:

This work shall consist of removal and salvage, disposal or relocation of various existing improvements, such as pavement, structures, pipes, headwalls, curbs and gutters, riprap, fences, mailboxes and other items necessary for the accomplishment of the improvements.

Where the items are identified to be salvaged, the CONTRACTOR shall deliver the item to a location to be determined by the Town of Queen Creek. The location for salvaged item delivery shall not be located more than 5 miles from the project site.  Where salvage items are to be re-installed on site, they shall remain on site.

350.3 Miscellaneous Removal and Other Work

Section 350.3 of the MAG Standard Specifications is modified to add the following:

- Remove and replace existing upper barrel of fire hydrant, rotated so that the pumper nozzle is facing due east.

- Remove, salvage and replace existing backflow preventer.

- Remove and replace existing vertical curb or curb and gutter; replacement shall be made per Section 340 and to the nearest joint.

- Remove and replace existing valley gutter; replacement shall be made per Section 340 and to the nearest joint.

- Remove and replace existing sidewalk; replacement shall be made per Section 340 and to the nearest joint.

- Other items identified for removal and replacement that are not specifically identified above shall be replaced in accordance with the associated specification section(s) for new construction.

- Sign removal includes sign panels, post, foundation, and associated hardware within the right of way. Signs designated to be relocated shall be carefully stockpiled or stored by the CONTRACTOR.

- Signs designated to be removed shall be carefully removed and delivered at no additional cost to the Town Street Department at the Corporation Yard on Queen Creek Road between Signal Butte Road and Meridian Road.  The CONTRACTOR shall contact Tony Garcia at (480) 358-3823 or Jan Martin at (480) 747-0583 to make arrangements for delivery to the Town.

- Signs that are to be salvaged or relocated and are damaged or destroyed as a result of the CONTRACTOR’s operations shall be repaired or replaced by the CONTRACTOR at no additional cost to the Town.

- Holes, cavities and depressions resulting from the removal of posts and post bases shall be backfilled with suitable earthen material which shall be compacted to a density of not less than 95 percent.

Where relocation of fence involves chain link fence, new posts shall be provided and installed by the CONTRACTOR unless otherwise noted.  All relocated chain link fence shall be re-installed in accordance with MAG Specification 420 with new materials provided for all ties, clips and other hardware and foundations beyond the salvaged wire fabric.

350.4 Payment

Section 350.4 of the MAG Standard Specifications is modified to add the following:

Payment for removals are noted below and shall constitute full compensation for furnishing all material, labor, tools and equipment and accomplishing all work associated with removing said items as described in the special provisions and on the construction plans.

Payment for salvaged and re-installed fence shall be per unit price per linear foot and shall include full payment for all new and salvaged materials, hardware, wire ties, clips, posts, post foundation concrete, post excavation and other incidental materials, labor, tools, equipment and other items and efforts to perform the work.

The relocation of the video detection system, if so included on project, shall include relocating the video detection camera, mounting pole and hardware, and placing them on the new mast arms per the Town of Queen Creek Standard Details and requirements. The Contractor shall furnish and install all new manufacturer approved cable which runs unspliced from the controller to the camera.

Any reusable traffic sign and signal salvage items will be delivered to the Town of Queen Creek Public Works yard for work within the Town Limits.  Any reusable traffic signs on Germann Road, within Maricopa County Limits will be delivered to the County at the appropriate facility.  Some traffic signs noted for removal and salvage on Germann Road are mounted directly on Utility posts, in these cases; there will be no post removal.

ITEM 350.xxxxx	RELOCATE eXISTING FENCE	LF

item 350.xxxxx	relocate existing traffic sign	ea

ITEM 350.xxxxx	Remove Existing AC Pavement	SY

item 350.xxxxx	remove existing concrete curb and gutter	lf

item 350.xxxxx	remove existing concrete headwall	lf

item 350.xxxxx	remove existing irrigation ditch	lf

item 350.xxxxx	remove existing irrigation structure	ea

item 350.xxxxx	Remove existing sign and post	ea

item 350.xxxxx	remove existing pipe, bleed-off	lf

item 350.xxxxx	remove existing pipe, irrigation	lf

Payment for remove and salvage items are noted below and shall constitute full compensation for furnishing all material, labor, tools and equipment and accomplishing all work associated with removing said items as described in the special provisions and on the construction plans.

item 350.xxxxx	remove and salvage existing chain link fence	lf

item 350.xxxxx	remove and salvage existing gate	ea

item 350.xxxxx	Remove and Salvage Existing Traffic Signal Equipment	LS

PART 400 – RIGHT-OF-WAY AND TRAFFIC CONTROL

SECTION 401 TRAFFIC CONTROL

401.2 Traffic Control Devices

Section 401.2 add the following:

All traffic control devices and their application shall conform to the Manual on Uniform Traffic Control Devices (MUTCD) handbook and current revisions (United States Department of Transportation, Federal Highway Administration), the special provisions and any field modifications made by the Town Traffic Engineer or designee.

All traffic control devices shall meet the guidelines of NCHRP 350.

401.2.1 Temporary Traffic Control Devices

It shall be the responsibility of the CONTRACTOR to provide, erect, maintain, remove and/or relocate all temporary and existing traffic control devices and signal indications necessary to properly mark and control the construction area(s) for the safe and efficient movement of all roadway users.

The CONTRACTOR shall provide additional devices as determined by the Town Traffic Engineer or his/her designee, to safely control traffic.

The Town Traffic Engineer, or designee, reserves the right to make contact with the traffic control subcontractor at any time to request any materials or services deemed necessary for the safety of the public or workers. The cost of these materials or services shall be included in the cost of Traffic Control.

The CONTRACTOR shall install temporary traffic control warning signs and devices prior to the start of any work in accordance with the approved Traffic Control Plan (TCP).  Each 600 feet point of the project shall be signed with construction speed limit signs, placed at locations where the need for relocation during construction is minimized.  Placement of construction speed limit signs shall be omitted along Crismon Road and 220th Street.

All temporary traffic control devices shall be ballasted with sandbags or other approved ballast.   The amount of sandbags used shall be enough to provide adequate safety for the traveling public and resist wind blown overturning.  The CONTRACTOR shall mount signs on wind resistant, spring-type bases.  The CONTRACTOR shall place flags above all temporary construction signs.  The CONTRACTOR shall use warning lights to mark traffic control devices at night.  The CONTRACTOR shall mount Type B high-intensity flashing warning lights on all advanced warning signs within the work zone.

The CONTRACTOR shall use an arrow board for all stationary or moving lane closures.  The CONTRACTOR is responsible for all costs incurred in replacing all lost or damaged traffic control devices and traffic control warning signs.

Portable concrete barrier (PCB) installations shall be in accordance with Chapter 9 of the AASHTO Roadside Design Guide.  The PCB shall use F-shape faces.  Each section shall be properly connected to the adjacent section to provide barrier continuity to resist movement, snagging, and/or instability of impacting vehicle.  PCB panels and connections shall meet NCHRP 350 Test Level 3.

401.2.2 Pavement Markings

Pavement markings used as an integral part of the traffic control plan shall be kept distinct and visible during their use.  Temporary pavement markings shall match and meet the markings in place at both ends of their usage.  Conflicting existing pavement markings or prior temporary markings shall be obliterated to prevent driver confusion.

401.3 Flagmen or Pilot Cars

Section 401.3, add the following:

All  flaggers  shall  be  properly  trained  and  certified  by  either  the  International  Municipal  Signal Association (IMSA), or American Traffic Safety Services Association (ATSSA) and shall carry proof of training with them at all times. Flaggers shall use “STOP/ SLOW” paddles to control traffic; orange construction flags are not permitted.

401.4 Traffic Control Measures

Section 401.4, add the following:

401.4.1 Traffic Control Plan

Construction shall not commence without an approved Traffic Control Plan (TCP).  At the time of the pre-construction meeting, the CONTRACTOR shall submit a proposed TCP for each phase of the work to the Town for approval and permit according to the Town established procedure.  Plans shall be of an appropriate size and legible.   Plans found to be deficient by the Town Traffic Engineer shall be returned for correction.  The CONTRACTOR shall design the traffic control plan using the posted speed limit existing prior to work starting as the design speed.  The TCP shall show all striping, signing, barricading and distances for all devices for all movements of roadway users during each phase of construction.   The signing shall show both existing and temporary construction signs, identify conflicting signs to be covered/removed or relocated, and identify other features that may conflict with the placement of temporary signage.   The TCP shall also show the duration with the start and end date of each phase. The TCP shall include all requests for lane closures or restrictions per requirements in section 105.5.1.

401.4.2 Traffic Control Technician

No Traffic Control Technician is required for this project.

401.4.3 Intersection Restriction

Off-duty  Queen  Creek  District  Maricopa  County  Sheriff’s  Office  deputies  are  required  during  any construction activity that requires interaction of construction equipment or vehicles with the open flowing traffic.  Contact Sgt. Dan Jones Patrol/Administrative Sergeant at either (480) 861-8771or at Daniel_Jones@mcso.maricopa.gov for scheduling.  A minimum of 24 hours of notice is required.

401.4.4 Traffic Control Devices

The CONTRACTOR shall provide and maintain all necessary traffic control devices until acceptance of the project by the Town.

All signs shall be equipped with two orange construction flags, except “End Road Work Thank You” sign, unless noted otherwise.  All construction warning signs shall have a black legend on an orange fluorescent background unless otherwise noted.  The mounting height for embedded post mounted signs shall be a minimum of seven feet, and the mounting height for portable stand (rigid and spring) mounted signs shall be a minimum of five feet, measured from the bottom of the sign to the near edge of pavement elevation.

Type “A” flashing warning lights shall be required on all nighttime construction signs except the “End

Road Work Thank You” sign.

For signs installed on embedded posts, the nearest edge or corner of a sign should be seven feet from the nearest edge of pavement.

With the exception of advance construction zone signing, when traffic control devices are not in use, they shall be moved at least 10 feet from the roadway and turned away from traffic so the legend is not visible to the public.  This includes sign supports without sign panels.  Any signs which are not in use but which cannot be moved at least 10 feet from the roadway shall be covered or turned away so the public cannot read the legends.

All existing signs in conflict with the construction signs shall be covered in place, as directed by the Town Traffic Engineer.  The CONTRACTOR shall store and reinstall items which have been removed or relocated in a manner approved by the Town Traffic Engineer.  The cost shall be considered as included in the price of the contract items.

Construction signs and changeable message boards, except advance construction zone signing, shall not be displayed to traffic more than 72 hours prior to the start of construction, except as required by the Town.  These signs may be installed sooner but, if so they shall be covered or turned away from traffic.  The cost for covering or turning them shall be considered part of the sign installation cost.  No further compensation will be made.  These signs shall be removed within 24 hours after the completion of the construction activities.  Advance construction zone signs shall be displayed a minimum of three (3) days prior to the start of construction activities.

Vertical panels or Type II barricades shall be placed on all taper and tangent sections of the traffic control during construction.  A Type “C” steady-burning yellow light shall be mounted on every vertical panel or Type II barricade during nighttime activities to delineate the edge of traveled way.

The retroreflective sheeting on all traffic control signs, barricades, vertical panels, and other work zone traffic control devices except orange signs shall meet the criteria established for Type IV, Type VIII, Type IX, or Type XI sheeting in ASTM D4956-07.  All orange signs shall have fluorescent reflective sheeting and shall meet the criteria established for Type VIII, Type IX, or Type XI sheeting in ASTM D4956-07.  All sign panels and their supports shall be installed to meet the current crash testing requirements.

All construction access and staging areas shall be located within the existing right-of-way or easement for the length of the project.

401.4.5 Flaggers

All flaggers shall be properly trained and certified by either the International Municipal Signal Association (IMSA), or American Traffic Safety Services Association (ATSSA) and shall carry proof of training with them at all times.  Flaggers shall use “STOP/ SLOW” paddles to control traffic; orange construction flags are not permitted.

401.4.6 Failure To Provide Adequate Traffic Control Measures

If the CONTRACTOR fails to provide adequate traffic control measures, the Town may have the work accomplished by other sources.  The cost of having this work accomplished by other sources will be computed in accordance with Section 109.5.  The total cost will be deducted from monies due or to become due to the CONTRACTOR.

401.5 General Traffic Regulations

Section 401.5, add the following:

401.5.1 Road Closure and Road Restrictions

A road closure for the convenience of the CONTRACTOR is not authorized without Town approval and must be demonstrated to be required for construction and traffic safety.

No roadway closures or lane closures will be allowed during holidays or special event periods, unless otherwise approved by the Town Traffic Engineer.

The CONTRACTOR shall notify and coordinate with the Town Traffic Engineer at least 10 working days prior to any lane closures.  Coordination may consist of obtaining permits, approval of work zone limits, duration of construction, special events or other concerns presented by the Town Traffic Engineer.  The CONTRACTOR is responsible to obtain all necessary permits prior to commencing work.

401.5.2 Minimum Lane Requirements

The CONTRACTOR shall develop traffic control plans to maintain a minimum of one lane of travel in each direction for existing paved streets.  At signalized intersections, left turn lanes shall be maintained open when possible.  Left turn prohibitions shall require Town Traffic Engineer approval prior to construction.  Such approval is at the sole discretion of the Town.  Minimum lane requirements may be modified by Section 105.5.1.  Closure of 220th Street for construction shall be north of the Barney Sports Complex Driveway thereon.

401.5.3 Temporary Lane Diversions

For construction or trenching that requires movement of traffic from the normal travel lanes, temporary lane diversions may be used only during daylight hours and the normal traffic lanes shall be restored prior to the end of daylight hours.  Traffic plates and temporary pavement shall be used to restore traffic lanes.  The Town Project Manager or the Town Traffic Engineer, under unusual conditions, may authorize exceptions.

401.5.4 Regulatory Speed Limit Signs

An appropriate regulatory speed limit sign shall be used where traffic is maintained on temporary detour roads, diversions, or on traffic lanes that are severely restricted.

401.5.5 Signal Equipment Repair

If existing signal equipment is damaged, the CONTRACTOR shall immediately notify the Project

Manager, in order to facilitate the prompt restoration of the traffic signal operation.  All costs associated with the repair of damaged traffic signals caused by CONTRACTOR construction activity shall be borne by CONTRACTOR.

401.5.6 Portable Concrete Barriers / Steel Plating

Open excavations and trenches within 10 feet of an active traffic lane shall be protected at night and during non-working days from vehicle traffic by steel plating or the use of portable concrete barriers. Open excavations as may occur with reinforced concrete box culvert construction and other work shall require portable concrete barriers to separate vehicle traffic from the work site.  The CONTRACTOR shall use Portable Concrete Barrier when construction hazards warrant, or as requested by the Town Traffic Engineer.  Impact attenuation devices shall be provided by the CONTRACTOR commensurate with concrete barrier requirements.

401.5.7 Temporary Fencing

Contractor shall provide and install minimum 6 feet tall temporary chain link fencing across the Ryan Road and adjacent SRP easement alignment from existing or temporary nursery fence to the solar site fence to provide security until the fence along Ryan Road has been re-installed. The fence shall be provided at both the eastern and western ends of the corridor.  A gate for Contractor and Town access shall be provided at each end of the Ryan Road corridor and secured with a lock when work is not underway. Contractor shall provide and install temporary chain link fencing along any reaches of fencing being relocated or re-installed to provide security.  Such fencing may be provided in short reaches as needed and moved along with the work as work progresses.  Gate sections shall be provided as needed for access and coordinated with the Town.

CONTRACTOR shall install temporary fencing along excavation or work zones where pedestrian traffic is expected or observed to pass or as directed by the Town.  All sidewalks affected by the project shall be marked as closed until passage is available.  The Town may require alternative pedestrian routes to be created for the Crismon intersection.

401.6 Measurement

Section 401.6 is replaced with the following:

Measurement for Traffic Control shall be made on an Allowance basis. This item shall include all materials, equipment and labor necessary to facilitate traffic control per the contract documents.  Items of Traffic Control  include,  but  are  not  limited  to,  the  obliteration  of  existing  and  temporary  pavement markings or markers, portable or temporary traffic signal equipment, pilot cars, flagmen, barricades, sign panels, sign stands, warning lights, and related temporary pavements, and off duty officers.

401.7 Payment

Section 401.7 is replaced with the following:

Payment for Traffic Control and Uniformed Off-duty Law Enforcement Officers will be billed against allowance items 109.40110 Traffic Control and 109.40120 accordingly.

Payment for Barricades, will be made at the contract unit price per linear feet, and shall constitute full compensation for furnishing all material, labor, tools and equipment and accomplishing all work associated with installing the barricade complete in place as described in the special provisions and on the construction plans.

item 401.xxxxx	barricade, adot std. s-17”ROAD CLOSED”	LF

ITEM 401.xxxxx	Barricade, MAG Std. Det. 130, Type A	LF

Payment for Temporary Fencing will be made at the contract unit price per linear feet and shall constitute full compensation for furnishing all material, labor, tools and equipment and accomplishing all work associated with installing the temporary chain link fencing as described in the special provision.

Payment for other construction fencing or pedestrian routes, if requested by the Town, shall be provided under the traffic control allowance.

item 401.xxxxx	Temporary fencing, chainlink	lf

SECTION 405	MONUMENTS

405.5 Payment

Section 405.5 of the MAG Standard Specifications is modified to add the following:

# Payment for placing survey monuments will be made at the contract unit price per each, and shall constitute full compensation for furnishing all material, labor, tools and equipment and accomplishing all work associated with placing the survey monuments complete in place as described in the special provisions and on the construction plans.  Additionally, a new Arizona Land Survey Corner Record shall be recorded with the Maricopa County Recorder by the Contractor’s RLS.  A copy of the recorded document(s) shall be provided to the Town.

ITEM 405.xxxxx	Survey Marker, MAG Std. Det. 120, Type A	EA

SECTION 430	LANDSCAPING AND PLANTING

Landscaping and planting shall conform to Section 430 of the MAG Uniform Standard Specifications except as modified herein.

430.1 Description

Modify the first paragraph to read:

Section 430.1 of the MAG Standard Specifications is modified to add the following:

The work under this section shall consist of furnishing all labor, materials, and equipment to install decomposed granite, trees, plant material , boulders, rock mulch and monument signage as designated for installation on the project plans.

Modify the second paragraph to read:

Existing utilities and improvements not designated for removal or relocation shall be protected in place. Determine the location of underground utilities (call Blue Stake) and perform all work in a manner which will avoid possible damages to the utility. The Contractor shall repair any damages at no additional cost to the Owner. Hand excavate around utilities as required.

430.2 General

Section 430.2 of the MAG Standard Specifications is modified to add the following:

The Contractor shall furnish all labor, materials, equipment, and incidental and appurtenant items of work needed to install the landscape, to the extents and details shown in the plans.

430.2.1 – Repair of Existing Landscape Areas:

Add entire subsection:

The project work includes the addition of sidewalks, ramps and curb and gutter, box culverts and installation or replacement of underground utilities including water, irrigation and various electrical and communication lines. The installation of these new curb and gutter, sidewalk sections, box culverts and underground utilities will impact existing landscape and irrigation systems. It is anticipated that the removal and forming of the new box culvert, headwalls, wing walls and channel grading will disturb the existing landscape and irrigation at existing retention basins. The CONTRACTOR shall make the necessary landscape and irrigation repairs necessary to restore the landscape areas disturbed by the curb and walk installations.

The CONTRACTOR and the Town representative shall inspect all landscape and irrigation that is expected to be impacted prior to the start of construction activities. The purpose of the inspection will be to establish the existing condition of the landscape and irrigation systems. This inspection shall set a minimum level of performance that the CONTRACTOR shall meet with the restoration activities.

The landscape repairs will consist of plant replacement, decomposed granite or river rock installation, boulder relocation, concrete header saw cutting, repair or replacement. Salvage and replacement of existing granite is an acceptable alternative to installation of new granite.

The irrigation repairs and replacement will consist of drip emitter and distribution line adjustment, drip PVC and poly lateral line adjustment, and adjustment to existing turf spray heads, remote control valves with wye filters, pressure regulators and valve boxes for drip systems, turf control valves with valve boxes, as well as adjustment or relocation of other existing spray heads to minimize overspray. No heads shall spray over sidewalk towards roadway.

Landscape rock materials shall match the existing color and gradation. New plant materials shall be sized as follows ground covers- 1 gallon, shrubs- 5 gallon, trees- 36” box (with dual 2” diameter lodge pole pine stakes). Turf, shall be by seeded hybrid Bermuda.

Irrigation equipment shall be commercial grade equal to or better than that which is existing.  All new sprinkler piping shall match existing pipe sizes and material. Any new pipe shall be schedule 40 PVC. All fittings shall be schedule 80 for mainline or schedule 40 for lateral lines. All remote control valve wiring shall be 14 AWG UF-600 for direct burial. Wire splices shall be Dri-splice. All emitters shall be pressure compensating. Turf spray heads shall be 4” pop-up RainBird 1804 or equal.

CONTRACTOR shall operate all irrigation within and around all disturbed construction areas to confirm both new and existing irrigation is operational (existing irrigation as determined to be operational prior to construction only) by controllers and emitting water to all plants and grass without leaks or excessive overspray.

All repair of existing landscape areas shall be guaranteed for one year from the time of project acceptance.

All areas where repairs occur shall be swept clean and washed down by hose prior to final acceptance.

See Plans for the locations of proposed improvements.  Existing landscaped areas adjacent to all these locations shall be restored or repaired to the satisfaction of the private property owner (if applicable) and the Town Project Manager.

430.4 Decomposed Granite:

Delete in its entirety and replace with:

A. Decomposed Granite

- Decomposed granite shall be native, local, desert, decomposed granite stone at the size and color specified on the plans.  The decomposed granite shall be from a single source, free from coating, clay, caliche or organic matter. Contractor shall provide Town Inspector with a sample of material for approval before installation. Multiple samples may be required.

- Contractor must examine the subgrade, verify the elevations, and observe the conditions under which the work is to be performed.  The existing grade shall be fine graded and raked free of organic matter and other debris 1-inch diameter and larger.  Contractor shall apply one application of pre-emergent herbicide as per manufacturer’s directions prior to installing granite, one application after granite has been installed, compacted and raked level and one application 30 days prior to the end of the maintenance period.  The Town Inspector is to be notified prior to all pre-emergent applications.

- Installed granite shall be raked to remove any irregularities.  Installation shall provide a minimum two-inch depth of decomposed granite after compacting.  Methods of compacting such as rolling, etc., shall be approved by the Town Inspector.  Unless otherwise specified in the drawings, granite finish grade shall be one (1) inch below top of curb or adjacent sidewalk surfaces.

- All disturbed (non-seed) areas shall be treated with a pre-emergent weed spray "Gallery", or an approved equal. In addition, any existing weeds or Bermuda grass shall be treated with a post-emergent spray, such as “Round-up”, or an approved equal. Any existing or new trees, vegetation or adjacent crops shall be protected from the spray drift. There will be no separate payment for the weed spraying.  Bermuda grass or weeds must be completely eradicated where designated by the Engineer from landscape, sand or decomposed granite areas.

430.4.1 Decomposed Granite 1/2-Inch Screened: Contractor shall supply and place decomposed granite in areas designated on the plans. Gradation requirements for the Items Decomposed Granite 1/2” Screened and Decomposed Granite to Match Existing Off-site Granite are as follows:

Decomposed Granite 1/2 Inch Screened

| Sieve Size | Percent Passing |
| --- | --- |
| 1/2 Inch | 100 |
| 1/4 Inch | 50-60 |

| Decomposed Granite to Match Existing Off-Site Granite |  |
| --- | --- |
| See Plans |  |

Contractor shall provide 1 gallon volume samples to the Town of Queen Creek for all granite specified for approval by Town Representative and Landscape Architect prior to placement.

All disturbed areas shall be treated with a pre-emergent per the plans and details and any active weed growing area with a post-emergent spray, such as “Round-up” or an approved equal. There will be no separate payment for the weed spraying.  Bermuda grass or weeds must be completely eradicated where designated by the Town of Queen Creek from landscape or decomposed granite areas. All weed control products and the Town of Queen Creek shall approve herbicides for use prior to any applications. Contractor shall submit copies of all manufacture specifications and application rates to the Town for review and approval prior to application. Herbicides and weed control shall only be performed by a licensed applicator; Contractor shall supply information on applicator to the Town of Queen Creek for approval. Contractor shall apply two applications of pre-emergent herbicide- the first at the time of granite installation and the second within one week prior to the end on the maintenance period. The Contractor shall contact the Engineer prior to herbicide application so that the Engineer can inspect the proper mixing and application of the herbicide. The Contractor shall guarantee a weed free condition will exist for a 6 month period following the end of maintenance of the project. Should any weeds occur the Contractor shall remove and dispose of all weeds and reapply the pre-emergent herbicide again at no cost to the Town. The Contractor shall again guarantee a weed free condition for an additional 6 months.

430.4.2 Salvage and Replace Existing Granite

CONTRACTOR shall salvage and replace decomposed granite in areas the fill slope overlaps existing landscaped areas.  Granite shall be installed so that the finish grade of the top of the granite is 1” below the top of adjacent walks, driveways and ramps.  Granite shall be installed per section 430.4 paragraphs above.

430.4.3 New Decomposed Granite to Match Existing

CONTRACTOR shall install new decomposed granite in areas designated on the plans as “2” Deep Decomposed Granite”. The granite shall match the existing granite in color and gradation. The CONTRACTOR shall provide a 1 gallon bucket as a sample to the Town representative for approval prior to installation.  Multiple samples may be required.  Granite shall be installed so that the finish grade of the top of the granite is 1” below the top of adjacent walks, driveways and ramps.  Granite shall be installed per section 430.4 paragraphs above.

430.10 Payment: is modified to add:

Payment for ½” screened Decomposed Granite (Date Gold), 2” Thick shall be at the contract unit price per square feet for all areas of new installation.  The unit price shall be considered full compensation for the complete in-place placement and shall include all cost, materials, equipment, labor and operations necessary as described herein and on the project plans.

Payment for areas of restoration of landscaping, irrigation and decomposed granite as shown on the project plans shall be paid at the contract unit price per Lump Sum for all areas where new improvements encroach into existing landscaped areas adjacent to the project.  Additionally, all landscape, irrigation and granite on the Barney Sports Complex that is disturbed by the trenching, installation and backfilling required for ITS conduit as shown on the project plans shall be paid for at the contract unit price per Lump Sum and shall constitute full compensation for furnishing all material, labor, tools and equipment and accomplishing all work associated with restoring these disturbed areas to the original pre-construction condition.  All irrigation within the disturbance area shall be tested to assure it is fully operational.

item 430.21000	restore landscaping, irrigation and decomposed	ls

granite

item 430.42010	Decomposed Granite - 1/2" – Screened, (2" Thick)	SF

SECTION 460	REMOVAL OF PAVEMENT MARKINGS AND RAISED PAVEMENT MARKERS

This section per the MCDOT supplement to the MAG Standard Specifications, modified below:

460.1 Description

The Contractor shall furnish experienced supervision, labor, all materials, equipment, tools, transportation and supplies required accomplish the pavement marking removal in accordance with these specifications, where indicated on the Striping Plans, or where determined by the Engineer.

460.2 Construction

The Contractor shall determine the type of pavement markings that exist in the field and the appropriate removal methods specified in this Section.

Existing traffic pavement markings shall not be covered over with slurry seal, black paint or stain of any kind. The Contractor shall accomplish pavement marking obliteration as per the requirements indicated on the Plans or where determined by the Engineer. The Contractor shall be responsible for verifying the striping removal limits of the project before commencement of the work. The striping removal limits may exceed the construction project limits, or new striping limits in order to match and tie into the existing striping.

Existing pavement markings shall be removed to the fullest extent possible from the pavement by one of the methods identified in this Section, unless another method is approved by the Engineer. The method used shall not materially damage the surface or texture of the useable pavement. Sand or other material deposited on the pavement as a result of removing pavement markings shall be removed as the work progresses. Accumulations of sand or other material, which might interfere with drainage or might constitute adverse safety conditions to traffic, will not be permitted.

Where blast cleaning is used for the removal of pavement markings or for removal of objectionable material, the residue including dust shall be removed immediately after contact between the sand and the surface being treated. Such removal shall be by a vacuum attachment operating concurrently with the blast cleaning operation, or by other methods approved by the Engineer. Blasting shall not be used within 12 ft. of a lane occupied by traffic.

Any damage to the pavement caused by pavement marking removal shall be repaired by methods acceptable to the Engineer. When asphalt slurry is used to repair damage to the pavement caused by pavement marking removal or the obliteration of the marks remaining after the markings have been removed, the asphalt slurry shall be placed parallel to the new direction of travel and shall not be less than two feet in width.

460.2.1 Approved Methods of Removal

The following methods have been approved by the County for the removal of traffic paint, thermoplastic markings, Type 1 (Permanent) performed plastic tape, raised pavement markers and barrier/guardrail markers.

460.2.1.1 Traffic Paint

  - Sandblasting

  - Turbo-blaster (Steel shot method)

  - Chip Seal: When using this method, the entire roadway surface, edge of asphalt to edge of asphalt, shall be covered.

  - Asphalt Overlay: The asphalt overlay thickness and dimensions shall meet County specifications.

460.2.1.2 Thermoplastic

- Grinding followed by sandblasting.

- Chip Seal: The application of this method depends on the length of time the Thermoplastic Marking has been on the roadway surface. The use of a chip seal before grinding / sandblasting is at the discretion of Contractor. If the chip seal does not adhere to the existing thermoplastic markings, the Contractor shall grind and / or sandblast the thermoplastic markings off and chip seal the exposed area. All costs for this work shall be borne by the Contractor.  When applying chip seal, the entire roadway surface, edge of asphalt to edge of asphalt, shall be covered.  Chip seal shall not be applied to a Portland cement surface.

- Asphalt Overlay: The asphalt overlay thickness and dimensions shall meet the County specifications.

460.2.1.3 Type I - Preformed Plastic Pavement Marking Tape

- Grinding

- Chip Seal: The application of this method depends on the length of time the Tape has been on the roadway surface. The use a chip seal before grinding is at the discretion of Contractor. If the chip seal does not adhere to the existing tape markings, Contractor shall grind off the tape markings and chip seal over the exposed area. All costs for this work shall be borne by the Contractor.  When applying chip seal, the entire roadway surface, edge of asphalt to edge of asphalt, shall be covered.  Chip seal shall not be applied to a Portland cement surface

- Asphalt Overlay: The asphalt overlay thickness and dimensions shall meet the County specifications

460.2.1.4 Raised Pavement Markers

- Hammer and Chisel

- Blade (Use of Heavy Duty Equipment)

460.2.1.5 Barrier Markers for Bridges, Concrete and Guardrail

- Hammer and Chisel

460.3 Measurement

Measurement for removing painted stripe, removing thermoplastic stripe and Type 1 –preformed plastic marking tape will be by the linear foot along the centerline of the pavement stripe to be removed. Skips in dashed lines will not be included in the measurement.

Measurement for removing striping with a plan width greater or less than the basic 4” wide stripe will be made by the following method:

Plan Width of Striping (inches) x Linear Foot

4.0 (inches)

Double marking lines, consisting of two 4” wide stripes will be measured as two individual marking lines. Crosswalk lines, stop bars, stop lines, gore lines, cross hatch lines, chevron lines and railroad marking transverse lines will be measured for centerline length and adjusted for widths other than 4” as defined above.

Thermoplastic pavement symbols and legends will be measured by each unit removed.

Measurement for the removal of raised pavement markers and barrier markers for bridges, concrete, and guardrail will be by the unit for each marker removed.

460.4 Payment

Payment for Removing Painted Stripe will be at the unit contract price per linear foot for the length of painted line applied to the nearest foot.

Payment for Removing Painted Symbols and Removing Painted Legends will be per each for each symbol or legend removed.

Payment for Removing Thermoplastic Stripe and Removing Type 1 – Preformed Plastic

Marking Tape will be per linear foot of striping removed.

Payment for Removing Raised Pavement Markers and for Removing Barrier Markers for Bridges, Concrete and Guardrail will be per each marker removed.

All damage to the surface of the road caused by pavement marking removal shall be repaired by the Contractor at his expense.  Sealant applied to all areas of pavement marking obliteration shall not be paid for separately, the costs being considered included in the Obliterate Existing Pavement Marking item.

ITEM 460.xxxxx	Obliterate Existing Striping	LF

SECTION 461	PAINTED PAVEMENT MARKINGS

The work under this section shall be per the MCDOT supplement to the MAG Uniform Standard Specifications for Public Works Construction and Town standard notes.

461.1 Description

The work under this section shall consist of cleaning and preparing the pavement surface, furnishing all materials, experienced supervision, labor, equipment, tools, transportation, supplies and applying white or yellow, water-borne, lead-free, rapid-dry traffic paint and reflective glass beads at the locations and in accordance with the details shown on the plans, MUTCD, the requirements of these specifications, or where determined by the Engineer.

461.2 Materials

461.2.1 Pavement Marking Paint

General:

All material used in the formulation of the pavement marking paint shall meet the requirements herein specified. Any materials not specifically covered shall meet the approval of the Engineer. Certificates of Compliance conforming to the requirements of Arizona State Department of Transportation Standard Specifications for Road and Bridge Construction 2000 edition, section 106-05 shall be submitted for each lot or batch of paint prior to its use.

461.3 Construction Requirements

The traffic paint and beads shall be placed on the pavement by a spray-type, self propelled pavement marking machine.

461.3.2 Application

The pavement surface shall be applied when the pavement surface is dry and the weather is not foggy, rainy, or otherwise adverse to the applications of markings. The surface shall be free from excess asphalt or other deleterious substances before traffic paint, beads or primer are applied. The Contractor shall remove dirt, debris, grease, oil, rocks or chips from the pavement surface prior to applying the markings. Any area that cannot otherwise be satisfactorily cleaned shall be scrubbed with a biodegradable chemical. The method of cleaning the pavement surface and removal of detrimental material is subject to approval by the Engineer and shall include sweeping and the use of high-pressure air spray.

Painting shall not be applied when the atmospheric temperature is below 50 F.

461.4 Measurement

Pavement marking paint will be measured by the linear foot along the centerline of the pavement stripe. Skips in dashed lines will not be included in the measurement. Length of pavement markings will be based on a 4-inch wide stripe. Measurement for striping with a plan width greater or less than the basic 4 inches as shown on the plans or requested by the Engineer will be made by the following method:

Plan Width of Striping (inches) x Linear Feet

4-inches

Symbols, legends, painted medians, painted curbing, and painted islands will be measured by each unit applied. Each legend, regardless of the number of letters, will be considered as a single unit.

No separate measurement will be made for cleaning and preparing the pavement surface, including abrasive sweeping and high-pressure air spray. The cost of disposal of excess materials, cleaning fluids, and empty material containers, will be considered as included in the contract items.

461.7 Payment

Pavement striping of the type specified, measured as provided above, will be paid for at the contract price per linear foot for the total length of painted line applied to the nearest foot, which price shall be full compensation for the work complete, including cleaning and preparing the pavement surface and glass beads, as described and specified herein an on project Plans.

ITEM 461.xxxxx	Paint Traffic Stripe - White 4"	LF

ITEM 461.xxxxx	Paint Traffic Stripe - Yellow 4"	LF

Pavement symbols and legends as provided above, will be paid for at the contract price for each painted symbol or legend, which price shall be full compensation for the work complete, including cleaning and preparing the pavement surface, and glass beads, as described and specified a herein and on the project Plans.

ITEM 461.xxxxx	Paint Symbol (Arrow)	EA

SECTION 462	THERMOPLASTIC PAVEMENT MARKINGS

462.1 Description

The work under this section shall consist of cleaning and preparing pavement surfaces and furnishing and applying either white or yellow paint or hot-sprayed thermoplastic reflectorized stripes or pavement markings to the prepared pavement at the locations and in accordance with the details shown on the project plans and the requirements of these specifications and the Special Provisions.

The work under this section shall conform to the requirements of Section 704 of the ADOT Standard Specifications for Road and Bridge Construction.

462.5 Payment

The accepted quantities of thermoplastic pavement markings of the type specified in the bidding schedule, measured as provided above, will be paid for at the unit price, complete in place, including pavement surface preparation and glass beads.

Pavement marking stripes will be paid for at the contract unit price per linear foot complete in place for the total length of lines applied to the nearest foot, including surface preparation. If the Engineer determines that additional striping beyond the project limits are required in order to tie into and meet the existing striping, then this striping will be paid for at the contract unit bid price for the total length of lines applied.

ITEM 462.xxxxx	Thermoplastic Traffic Stripe - White 4"	LF

item 462.xxxxx	thermoplastic traffice stripe - yellow 4”	lf

Thermoplastic pavement marking legends and symbols will be paid for at the contract unit price per each. Such payment shall be full compensation for furnishing all material, labor, tools and equipment and accomplishing the work associated with application of the legends and symbols to the pavement, including surface preparation, as described in the special provisions and on the construction plans.

item 462.xxxxx	Thermoplastic Arrow	EA

ITEM 462.xxxxx	THERMOPLASTIC bike lane symbol	EA

SECTION 463	RAISED PAVEMENT MARKERS

The work under this section shall conform to the requirements of section 463 of the MCDOT supplement to the MAG Uniform Standard Specifications for Public Works Construction.

463.1 Description

The work under this section shall consist of cleaning and preparing the pavement surface; furnishing all materials, equipment, tools and labor; and placing raised pavement markers of the type specified at the locations and in accordance with the details shown on the plans and the requirements of these specifications.

463.4 Measurement

Pavement markers will be measured as a unit for each marker furnished and placed.

463.5 Payment

The accepted quantities of pavement markers, measured as provided above, will be paid for at the contract unit price for the type designated in the bidding schedule, complete in place, including adhesive and surface preparation.

ITEM 463.xxxxx	Reflectorized Raised Pavement Marker - Type D	EA

ITEM 463.xxxxx	Reflectorized Raised Pavement Marker - Type g	EA

item 463.xxxxx	Reflectorized Raised Pavement Marker - Type h	EA

item 463.xxxxx	Reflectorized Raised Pavement Marker – adot, m-26	EA

One direction, flexible delineator, in-ground mount

SECTION 465	TRAFFIC SIGNS

Add this section to the MAG Standard Specifications:

465.1 Description

The work under this section shall consist of providing and erecting traffic signs; furnishing all materials, equipment, tools and labor; and placing and erecting traffic signs of the type specified at the locations and in accordance with the details shown on the plans and the requirements of these specifications.

The work under this section shall conform to the requirements the Town of Queen Creek signing and marking standards and sections 464 and 465 of the MCDOT supplement to the MAG Standard Specifications for Public Works Construction.

465.2 Material:

The MCDOT Supplement to the MAG Uniform Standard Specifications is modified to add:

All signs shall be faced on new 0.080 aluminum blanks.

Sheeting shall be ASTM Type XI for all permanent regulatory, warning, guide, information, and object marker signs (including legends and borders)

All warning signs (yellow series) shall be manufactured with ASTM Type XI 3M Fluorescent Yellow

4081 diamond grade reflective sheeting or approved equal.

Sheeting shall be manufactured by 3M Corporation or an approved equal with equal or greater warranty periods.  All signs shall be manufactured using matching components approved by the sheeting manufacturer.

All street name signs shall be constructed of pressure sensitive AST Type XI 3M White 4090 diamond grade reflective sheeting or approved equal.  All transparent acrylic, pressure sensitive film shall be 3M series 1177 green electro cut film or approved equal.  Signs shall be manufactured by applying white sheeting to the entire aluminum bank, then a green translucent pressure sensitive film containing the cut out street name is applied. This method results in a white legend on a green background.

All object markers shall conform to Section 703 of the ADOT Standard Specifications for Road and Bridge Construction, 2008 version, and ADOT Standard Detail M-23 and M-24

465.3 Payment

Payment for placing the permanent traffic signs will be made at the unit price per square foot of sign panel installed.  Such payment shall constitute full compensation for furnishing all material, labor, tools, and equipment and accomplishing all work associated with placing the permanent traffic signs complete in place as described in the special provisions and on the construction plans.

item 465.xxxxx	Flat Sheet Aluminum Sign Panel, high intensity Grade	SF

item 465.xxxxx	Flat Sheet Aluminum Sign Panel, Diamond Grade	SF

Payment for the permanent TAPCO® BlinkerSign® Flashing LED Stop Sign will be made at the unit price per each.  Such payment shall constitute full compensation for furnishing all material, labor, tools, and equipment and for accomplishing all work associated with placing this permanent LED Stop Sign complete in place as described in the special provisions and on the construction plans.

ITEM 465.xxxxx	Permanent Traffic Sign	EA

Payment for placing the perforated signs posts will be made at the contract unit price per linear feet. Slip bases and sign post foundations will be made at the contract unit price per each. Such payment shall constitute full compensation for furnishing all material, labor, tools and equipment and accomplishing all work associated with constructing the foundations and erecting the sign posts complete in place as described in the special provisions and on the construction plans.

ITEM 465.xxxxx	PERFORATED SIGN POst (2 s)	LF

ITEM 465.xxxxx	PERFORATED SIGN POst (2 1/2 s)	LF

ITEM 465.xxxxx	SIGN POst FOUNDATION	EA

SECTION 470 SRP Related Work

470.1 Description

The work under this section shall consist of furnishing and installing electrical conduit, ground rods, pull boxes, and wiring from sonotube to pull box, associated with SRP requirements to convert the existing 12kV overhead electrical to underground.  This work will include trenching, backfilling, excavation, grading for SRP concrete pads, placing and compacting backfill material in accordance with the locations shown on the SRP plans and for Work Order #TXXXXXXX.

470.2 Payment

Payment for the SRP related work will be made at the contract lump sum price and shall constitute full compensation for the work described above and as shown in the to be issued SRP plans including all incidentals necessary to complete the work including delivery, storage and handling of materials.  No separate measurement or payment will be made for the various types of means and methods that may be required for installation.

item 470.10000	SRP Related work	LS

SECTION 471	ELECTRICAL UNDERGROUND INSTALLATION

471.1 Description

Traffic Signal and Street Light Related Work:

This section per the ADOT Standard Specifications for Road and Bridge Construction Section 732, and the Town of Queen Creek Signal Requirements, as modified below:

The work under this item includes the furnishing and installation of new traffic signal pull boxes and traffic signal conduit. This work shall conform to Section 732 of ADOT Standard Specifications for Road and Bridge Construction and the Town of Queen Creek Signal Requirements.

- 471.2 Materials

- Section 471.2 of the MCDOT Supplement to the MAG uniform Standards Specifications is revised to add the following:

- 471.2.1 Electrical Conduit

- All conduit and conduit fittings shall be listed by UL, and conform to NEC standards.  Except as specified below, all conduits to be installed underground shall be rigid polyvinyl chloride (PVC) rigid nonmetallic type confirming to the requirements of UL 651 for Rigid Nonmetallic Conduit.  PVC conduit and conduit fittings shall be Schedule 40.

- All conduit and conduit fittings to be installed above ground shall be rigid metallic type manufactured of galvanized steel confirming to requirements of UL 6 for Rigid Metallic Conduit and to NEC standards.

- Conduits under existing streets and paved or concrete areas shall be directionally bored or drilled.

Spare conduits shall be provided with an insulated ground wire installed.

- 471.2.2 Conduit Warning Tape

Conduit warning tape shall be a four (4) mil inert plastic film specially formulated for prolonged use underground and shall be a minimum of 3 inches wide. All tape shall be highly resistant to alkalis, acid and other destructive agents found in the soil.

Tape shall have a continuous printed message warning of the location of underground conduits. The message shall be in permanent ink formulated for prolong underground use and shall bear the words, “CAUTION – ELECTRIC LINE BURIED BELOW” in black letters on a red background.

- 471.2.3 Bond Wire

- Conduit bond wire shall be a No. 8 AWG bare copper wire.

471.2.4 Pull Boxes

A polymer number 7 pull box with extension shall be utilized on the control cabinet corner. A polymer number 7 pull box shall be utilized on each corner. Each pull box shall contain a ground rod and shall be connected to the grounding system. All pull boxes and splice boxes shall be polymer, and provided with locking devices.

The words “QUEEN CREEK TRAFFIC SIGNAL shall be labeled on the pull box covers in 1 inch high letters on No. 7 and No. 9 pullboxes.  The words “QC ROADWAY LIGHTING” shall be labeled on the pull box covers in 1 inch high letters on No. 5 pullboxes.

Pull boxes shall avoid placement in sidewalk areas, where possible, and no pull boxes shall be located in a wheelchair ramp area designed for wheelchair travel (such as the ramp itself).

At the request of the Town, the Contractor shall furnish pull box plans and specifications. Chipped or cracked pull boxes, covers and extensions will not be accepted.

Conduits under existing streets and paved or concrete areas shall be directionally bored or drilled.

- 471.3 Construction Requirements

- 471.3.1 (A) General Requirements

- Conduit shall be furnished and installed at the locations and of the sizes shown on the Traffic Signal Plan.  Unless changes are necessary to avoid underground obstructions, all underground conduit shall be installed in a straight line from pull box to pull box and/or from foundation to pull box and shall be of one continuous size.  Any change in conduit routing must be approved by the Engineer and documented by the Contractor on as-built traffic signal plans.

- The PVC conduit shall be cut square and trimmed to remove all rough edges.  PVC conduit connections shall be of the solvent weld type.  Purple primer conforming to the requirements of ASTM F 656 shall be applied to the joined surfaces prior to use of cement.  The joint cement shall be the gray PVC cement conforming to the requirements of ASTM D 2564.  Where a connection is made to rigid metallic conduit, the coupling used shall be a PVC female adapter.

- Expansion joint fittings shall not be installed in PVC conduit runs between pull boxes unless specified.  Expansion joint fittings shall be installed in conduit runs in which both ends of the conduit are fixed in place, such as conduit runs between two foundations.  Expansion joint fittings shall be installed in conduit runs, which cross a concrete structure expansion joint.  Approved expansion fittings shall allow for a linear thermal expansion of up to 6 inches.

- Field PVC conduit bends shall be made without crimping or flattening, using the longest radius practical but not less than specified by the NEC, Article 347-13.  Collapsed conduit, no matter how small, is not acceptable.  The number of bends between pull boxes or between pull box and foundations shall not contain more than equivalent of two quarter bends (180 degrees, total), including the bends at the pull boxes or foundations, unless authorized by the Engineer.

- PVC conduit entering a pull box or foundation shall be fitted with a factory made 90 degree elbow with a minimum sweep radius per the table below:

| - PVC Size | - Radius |
| --- | --- |
| - 2 Inches | - 10 Inches |
| - 2 ½ Inches | - 11 ¼ Inches |
| - 3 Inches | - 13 Inches |

- Conduit shall enter pull boxes near the sides and ends and extend no more than 4” above the bottom of the pull box including the length of the conduit bell end.

- Conduit for future use shall have a ¼ inch nylon rope or a No. 8 AWG bare copper wire installed which extends 24 inches beyond each end of the PVC conduit run.  This pull rope or bond wire shall be coiled and inserted into the conduit so as to be easily recovered from either end.  Conduit ends shall be capped with conduit end cap fittings after the pull rope is installed.  Conduit end cap shall remain in place until wiring is started.

- The Contractor shall place warning tape (as specified in Section 471.2.2) in all open trenches in which conduit is placed.  All warning tape shall be buried at a depth of 6” to 8” below final grade.

- Where conduit is to be installed under existing roadway pavement by jacking or drilling methods, the jacking and/or drilling pits shall be kept 2 feet clear of the edge of the pavement.

- Existing underground conduit to be incorporated into a new system shall be cleaned and blown out with compressed air.

- Installation of conduit for underground electrical service shall be in accordance with the Traffic Signal Standards Drawings, as shown on the Traffic Signal Plan, and in accordance with the requirements of the utility company providing electrical service.

- 471.3.1 (B) Conduit Depth Requirements

- Conduit installed in protected areas such as behind curbs, under sidewalks, etc. that are not subject to any vehicular traffic shall be at a minimum depth of 36 inches below final grade.  Conduit installed under roadways, driveways or any open area where there is the possibility of vehicular traffic shall be installed at a minimum depth of 36 inches below final grade.  When conduit cannot be installed at the minimum depth, it shall be completely encased in 3” of class C concrete in accordance with MAG Section 725.

- 471.3.1 (C) Trenching, Backfilling and Compaction

Trenching shall be allowed only in unpaved areas, unless otherwise pre-approved, in writing, by the Town of Queen Creek Traffic Engineer. Trench warning tape, conforming to ADOT specifications and placement shall be utilized when conduit is installed in open trench. All Town of Queen Creek requirements shall be followed including installing ½ sack slurry throughout the entire trench up to the bottom of existing asphalt, see MAG “T TOP” trench details previously adopted by Queen Creek.

Open trench excavation across any existing paved areas, shall have two (2) parallel cuts made at a distance apart not to exceed 16 inches.  All removal and replacement of existing paved areas shall be in accordance with project details provided on the drawings.

All conduit and conduit fittings shall be listed by UL, and conform to NEC standards. Except as specified below, all conduits to be installed underground shall be rigid polyvinyl chloride (PVC) rigid nonmetallic type confirming to the requirements of UL 651 for Rigid Nonmetallic Conduit. PVC conduit and conduit fittings shall be Schedule 40.

All conduit and conduit fittings to be installed above ground shall be rigid metallic type manufactured of galvanized steel confirming to requirements of UL 6 for Rigid Metallic Conduit and to NEC standards.

Spare conduits shall be provided with an insulated ground wire installed.

The ITS conduit and DB120 for street lighting can be installed in a joint trench where running parallel on the same side of road on the plans.  See detail on plans.

Roadway Light Pole Pull Boxes:

CONTRACTOR shall install roadway lighting pull boxes. Roadway lighting pull boxes shall be installed per NEC standards and SRP requirements and standards.  Refer to the roadway lighting general notes and construction notes on the Roadway Lighting Plans for further requirements.  Each roadway lighting pull box adjacent to a roadway light pole shall be installed with a ground rod and #6 CU bond to pole including all ground clamps or CAD welds.

471.5 Payment

Payment for the installation of the underground conduit for the traffic signal, street lights and telecommunications will be made at the contract unit price per lineal foot. Such payment shall constitute full compensation for furnishing all material, labor, tools and equipment and accomplishing all work associated with installing the underground conduit complete in place as described in the special provisions and on the construction plans.

item 471.xxxxx	Flexible Conduit 1"	lf

item 471.xxxxx	directional drilling or boring for utility	lf

installations at existing improvements

Directional Drilling or Boring per MAG specification 608 may be used as an alternative to trenching and where designated for the installation of Traffic Signal and ITS conduits being installed under existing curb and gutter, sidewalks, and driveways where the Town of Queen Creek has indicated the existing improvements shall remain in place and as shown on the construction plans.

item 471.xxxxx	electrical conduit – schedule 40 pvc – 3” (trench)	lf

item 471.xxxxx	electrical conduit – sched. 40 pvc – 2-3” (directional BORE) LF

item 471.xxxxx	Electrical Conduit - Schedule 40 PVC - 2-3" (ITS) (Jt.trench)	lf

item 471.xxxxx	Electrical Conduit - DB120 PVC - 2-1/2" (Jt. Trench)	lf

item 471.xxxxx	Connect to existing ITS Conduit	LS

Payment for the installation of the traffic signal, street light, and telecommunications pull boxes will be made at the contract unit price per each. Such payment shall constitute full compensation for furnishing all material, labor, tools and equipment and accomplishing all work associated with installing the pull boxes complete in place as described in the special provisions and on the construction plans.

item 471.xxxxx	junction box, (SRP #UBJV4) (St. Light)	ea

item 471.xxxxx	pull box no. 7	ea

Item 471.xxxxx	Pull Box No. 7 w/Extension	EA

item 471.xxxxx	pull box no. 9 vault	ea

Payment for the installation of the ground rod with CU bond will be made at the contract unit price per each. Such payment shall constitute full compensation for furnishing all material, labor, tools and equipment and accomplishing all work associated with installing the ground rod complete in place as described in the special provisions and on the construction plans.

item 471.xxxxx	 5/8” x 8’ ground rod w/ #6 cu bond to pole (St. Light)	ea

SECTION 472	TRAFFIC SIGNAL AND ROADWAY LIGHTING FOUNDATIONS

Work under his section shall be in conformance with the ADOT Standard Specifications, modified as follows:

472.1 Description

This section per the ADOT Standard Specifications for Road and Bridge Construction Section 731, and the Town of Queen Creek Signal Requirements, as modified below:

The work under this item includes the installation of new traffic signal pole, control cabinet foundations, meter pedestal, street light and parking area foundations. This work shall conform to Section 731 of ADOT Standard Specifications for Road and Bridge Construction and the Town of Queen Creek Signal Requirements.

Where new traffic signal poles are to be installed next to existing sidewalk or new or existing curb ramps, the Contractor shall construct a new ADA accessible apron (a.k.a Concrete Apron) to provide access around the base of the pole as shown on the plans and details. The Contractor shall modify these details as necessary to accommodate any changed field conditions or variation in pole location at no additional cost to the Town.

Prior to pouring any concrete the Contractor shall contact the Town 48 hours in advance for an inspection. The measurement and cost associated with this item shall be incidental to the work associated with the construction costs of providing and installing the signal pole foundations.

Contractor shall not pour concrete foundations until foundation locations, elevations, and bolt pattern is inspected and approved by the Town.

The Contractor shall pothole all foundations for potential conflicts. The cost associated shall be considered incidental to complete the work associated with this item. Hand digging for potential conflicts is considered a form of pot holing and considered incidental to complete the work associated with this item.

Concrete samples shall be obtained each day of pouring for signal foundations.  All foundations shall be vibration poured.  Poles shall not be installed until concrete compressive strength test results are received and approved by the Town.  The Contractor is responsible for all the expenses for testing of concrete material for foundations. Concrete material testing will not be paid for separately and should be included in the unit price for foundation.

Pedestrian push buttons shall meet or exceed all ADA accessibility guidelines and shall be mounted 42 inches above the finished surface of the sidewalk according to the Town of Queen Creek Standard Details for Traffic Signal Construction.  Activation timing shall be determined and completed by the Town.

Roadway Light Poles:

Roadway light pole sonotubes furnished and installed by the CONTRACTOR for roadway lighting will be measured as a unit for each roadway light pole sonotube installed. All labor and materials for installing each roadway light pole sonotube, including, but not limited to, excavating, compacted backfill material around the pole, and restoration of affected area to original condition shall be included as part of the light pole unit of measurement.

Excavating and compacting backfill shall be in accordance with ADOT Standard Specifications and SRP requirements.

CONTRACTOR shall refer to the roadway lighting general notes, construction notes and details on the Roadway Lighting Plans to install street light poles.

CONTRACTOR shall coordinate with the Town of Queen Creek to install a unique street light number on each pole according to Town requirements.

CONTRACTOR shall coordinate with SRP to install a Hazardous Voltage Warning label on each pole according to SRP requirements.

472.5 Payment

The accepted quantities of foundations for signals, measured as provided above, will be paid for at the contract unit price per each, for the type of support or foundation designated in the bidding schedule, complete in place, which such price shall constitute full compensation for all of the work associated with constructing the foundations as defined on the project plans and in the specifications.  No direct measurement or payment will be made for signal cabinet, meter pedestal, or load center cabinet foundations, the cost being considered part of the related item.

item 472.xxxxx	6’-6” Sonotube for street light	ea

item 472.xxxxx	pole foundation, Type A	ea

item 472.xxxxx	Pole Foundation, Type R	EA

SECTION 474	TRAFFIC SIGNAL POLE INSTALLATION

474.1 Description

Work under this section shall be in conformance with the ADOT Standard Specifications for Road and Bridge Construction Section 731, and the Town of Queen Creek Signal Requirements, as modified below:

The work under this item includes the installation of new traffic signal poles, traffic signal mast arms, roadway street light poles, pedestrian light poles, and parking area poles. This work shall conform to Section 731 of ADOT Standard Specifications for Road and Bridge Construction and the Town of Queen Creek Signal Requirements.

474.7 Payment

Payment for traffic signal poles, mast arms, and roadway street light poles will be made at the contract unit price per each. Such payment shall constitute compensation in full for furnishing and installing said items complete in place as defined on the project plans and in the specifications.

item 474.20300	Traffic Signal Pole, Type A	ea

item 474.20600	Traffic Signal Pole, Type R	ea

item 474.30045	Mast Arm, 45 Ft	ea

SECTION 475	ELECTRICAL POWER SERVICE AND CONTROLLER CABINET INSTALLATION

475.1 Description

This section shall be per the ADOT Standard Specifications for Road and Bridge Construction Section 734, and the Town of Queen Creek Signal Requirements, as modified below:

The work under this item includes the installation of control cabinets, meter pedestals, and load center cabinets. This work shall conform to Section 734 of ADOT Standard Specifications for Road and Bridge Construction and the Town of Queen Creek Signal Requirements. Cabinet controller and Assembly material shall be in accordance with the Town of Queen Creek Approved Materials List.

The meter pedestal for the Traffic Signal shall be a combination battery backup unit and meter pedestal per the Town of Queen Creek Approved Materials List, Myers catalog # MEUG3A-2050-UPS-M100-AZ (MOD) or approved equal.  The foundation shall be construction in accordance with the ADOT Standard Details and Specifications.

The Contractor shall provide the traffic signal control and cabinet assembly. The type of controller shall be Cobalt/TS2. The type of cabinet is an ADOT Type IV, NEMA TS-2, Type 1 Econolite “Plug-n-Go”. The Controller shall include the Cabinet, controller, 12 load switches, Exterior generator power input plug, surge suppression, manual control handheld remote with detachable headphone jack, malfunction management unit. Foundation shall be constructed per ADOT Standard Details and Specifications.

The load center cabinet and foundation shall be in accordance with the ADOT Standard Details and Specifications.

Testing of the controller operation after installation shall be accomplished at the site. The Contractor shall be required to provide traffic control at the intersection with a uniformed off-duty officer during testing of the controller. Uniformed off-duty officers shall be obtained and scheduled through the Town of Queen Creek. Five (5) days notice is required to obtain a police officer.

A Town of Queen Creek representative will be present during all wiring operations and connections.

The Town of Queen Creek shall perform a one-month test of the controller operations before installation. The Contractor shall coordinate with Traffic Engineering at (480) 358-3003, a minimum of 48 hours, in advance of pickup of the controller/cabinet.

The Contractor shall notify the Town of Queen Creek Traffic Engineering representative at least five (5) days in advance of the scheduled traffic signal activation. Contact the Town Traffic Engineer at (480) 358-3003.

“Traffic Signal Control Change” ahead warning signs must be installed by the Contractor prior to turn on of each signal.

475.5 Payment

Payment for the installation of the meter pedestal and controller cabinet will be made at the contract unit price per each. Such payment shall constitute full compensation for furnishing all material, labor, tools and equipment and accomplishing all work associated with installing the meter pedestal and controller cabinet as described in the special provisions and on the construction plans.

ITEM 475.xxxxx	meter pedestal cabinet/BBS and foundation	ea

ITEM 475.xxxxx	controller cabinet ASSEMBLY (TS2 Plug and go)	ea

SECTION 476	SIGNAL INDICATIONS AND MOUNTINGS

Work under this section shall be in accordance with the ADOT Standard Specifications for Road and Bridge Construction Section 733, and the Town of Queen Creek Signal Requirements, as modified below:

476.1 Description

The work under this item includes the installation of traffic signal heads and mounting assemblies, and emergency pre-emption devices and systems.  This work shall conform to Section 733 of ADOT Standard Specifications for Road and Bridge Construction and the Town of Queen Creek Signal Requirements.

The Town of Queen Creek will provide all new red, yellow, green, and arrow LED signal heads and LED pedestrian heads and mounting assemblies. The Contractor shall provide all other labor, material, tool, and equipment necessary for installing signal and pedestrian heads provided by the Town.

Mounting holes for all traffic signal mounting brackets shall NOT BE drilled prior to standing the poles on their foundations, but shall be drilled once the poles are standing to ensure best mounting location.

Emergency Vehicle Preemption system shall consist of an optical emitter, optical detectors, detector cable, and phase selectors. The approved emergency vehicle, Tomar Strobecom II 4090-22-ST or 4090-1-ST Series Detectors, 4140 optical signal processor card, and two 700 Mini Strobes, and manufacturer approved cabling. The card shall be mounted in the detector rack provided with the signal cabinet. Preemption cables shall run unspliced from the sensor to the signal pole, to the controller cabinet terminals. Preemption devices shall be furnished and installed by the Contractor.

Traffic Mounting Assemblies shall be powder coat painted black per ADOT Standard Detail T.S. 9-0.

The detector shall be mounted approximately as shown in the plans and shall be compatible with the design and brand used by the Town of Queen Creek.

476.4 Payment

Payment for the installation of traffic signal faces and mounting assemblies will be made at the contract unit price per each. Such payment shall constitute compensation in full for installing the heads and assemblies defined on the project plans and in the specifications.

item 476.xxxxx	pedestrian push button w/sign	ea

item 476.xxxxx	Traffic Signal Indication Face	ea

(Pedestrian Man/Hand w/Countdown)

item 476.xxxxx	traffic signal indication face – type f	ea

item 476.xxxxx	Traffic Signal Indication Face - Type Q	ea

item 476.xxxxx	Traffic Signal Mounting Assembly (Type II)	ea

item 476.xxxxx	traffic signal Mounting Assembly (Type IV)	ea

item 476.xxxxx	traffic signal mounting assembly (type V)	ea

item 476.xxxxx	Traffic Signal Mounting Assembly (Type VII)	ea

item 476.xxxxx	Traffic Signal Mounting Assembly (Type XI)	ea

item 476.xxxxx	Remove & Relocate signal head w/ pelco mount	EA

Payment for the installation of the emergency pre-emption devices will be made at the contract unit price per lump sum. Such payment shall constitute full compensation for furnishing all material, labor, tools and equipment and accomplishing all work associated with installing the emergency pre-emption as described in the special provisions and on the construction plans.

ITEM 476.xxxxx	Emergency Pre-Emption System	ea

SECTION 477	INTERSECTION LIGHTING

477.1 Description

Traffic Signal Related Work:

Work under this section shall be in accordance with the ADOT Standard Specifications for Road and Bridge Construction Section 731, and the Town of Queen Creek Signal Requirements, as modified below:

The work under this item consists of the furnishing and installation of the luminaires and internally illuminated street name signs. This work shall conform to Section 731 of ADOT Standard Specifications for Road and Bridge Construction and the Town of Queen Creek Signal Requirements.

All luminaires are to be powder coated to match the color of the decorative bases and fixtures. The Contractor shall coordinate with the Town of Queen Creek to maintain paint color consistency.

Roadway Luminaire and street light poles:

CONTRACTOR shall furnish and install LED Roadway luminaires on traffic signal poles including luminaire mast arms.  Installation shall be per NEC standards.

CONTRACTOR shall furnish and install LED street lights including pole, arm, luminaire, and conductors from pull box to luminaire and fusing.  Installation shall be per NEC standards.  Refer to the roadway lighting general notes and construction notes on the Roadway Lighting Plans

Install the photocell on top of each luminaire and position the photocell facing north for controlling the luminaire.

477.5 Payment

Payment for the installation of the LED street light will be made at the contract unit price per each and shall include pole, arm, luminaire and conductors from pull box to luminaire and fusing. Such payment shall constitute compensation in full for furnishing and installing said items complete in place as defined on the project plans and in the specifications.

ITEM 477.xxxxx	13,500 lumen LED Street light: pole, arm, luminaire,	ea

& conductors

ITEM 477.xxxxx	9,500 lumen LED Street light: pole, arm, luminaire,	ea

& conductors

Payment for the installation of the luminaires and internally illuminated street name signs will be made at the contract unit price per each. Such payment shall constitute compensation in full for furnishing and installing said items complete in place as defined on the project plans and in the specifications.  Luminaires for the traffic signal pole installation shall include the plumbizer, finial, and hardware required to mount the luminaire.

ITEM 477.xxxxx	Luminaire, LED	ea

ITEM 477.xxxxx	Luminaire mast arm 20’	ea

item 477.xxxxx	Illuminated Street Name Sign	ea

SECTION 478	ELECTRICAL CONDUCTORS

478.1 Description

This section per the ADOT Standard Specifications for Road and Bridge Construction Section 732, and the Town of Queen Creek Signal Requirements, as modified below:

The work under this item includes the furnishing and installation of electrical conductors. This work shall conform to Section 732 of ADOT Standard Specifications for Road and Bridge Construction and the Town of Queen Creek Signal Requirements.

Electrical Signal Conductors

The Contractor shall not use either THHN or THHW wire.

Type XHHW or THW wire is acceptable in conduit.

All IMSA signal conductors shall be solid with the exception of 51-5 and 50-2.

Watertight fuses shall be utilized in the pull box adjacent to the luminaire pole.

Splicing for the (2) 25-Conductor cables shall be kept to a minimum and shall only take place in pull boxes. At no time shall any splices of any kind be allowed in conduit.

At pull box locations, all splices and cables shall be tagged and labeled per Town of Queen Creek requirements, which are as follows:

3M Scotchcote Wire Marker Tape, Panduit shall be used to indicate phase number and location as necessary.

Electrical service conductors shall be provided and installed by SRP.

One main signal common of adequate size (No. 8 AWG minimum size) to accommodate the electrical load of the installed signals plus all future signals hall run from the controller cabinet, around the intersection to each corner pull box. This conductor shall be stranded, with white insulation.

Video detection cables shall run unspliced from the hand hole at each pole to the controller cabinet. A manufacture supplied cable and pre installed connector shall be supplied for connection to the back of the camera down the pole to the hand hole then spliced into the cable from the signal cabinet. (Video detection splicing will only be allowed in the pole hand hole). Contact the Town for approved products.

Emergency vehicle preemption cable shall run unspliced from the controller cabinet to the senor. Absolutely NO SPLICES are allowed in preemption cables.

A No. 8 AWG solid copper conductor, with green insulation, shall be used in all PVC conduits containing electrical voltage circuits. Generally, the ground bond wires are connected together in each pull box, connected to the ground rod(s), and each pole to form a continuous grounded system.

478.5 Payment

Payment for the installation of the Traffic Signal electrical conductors will be made at the contract unit price per lump sum per each intersection with signal installation. Such payment shall constitute full compensation for furnishing all material, labor, tools and equipment and accomplishing all work associated with installing the conductors complete in place as described in the special provisions and on the construction plans.

item 478.xxxxx	Traffic Signal Conductors & Cables	LS

Payment for the installation of electrical service conduit for traffic signal will be made at the contract unit price per lump sum. Such payment shall constitute full compensation for furnishing all material, labor, tools and equipment and accomplishing all work associated with installing the electrical service for the traffic signals complete in place as described in the special provisions and on the construction plans.

item 478.xxxxx	Traffic Signal Electrical Service Conduit	ls

SECTION 483 CLOSED CIRCUIT TELEVISION

This section per the MCDOT supplement to the MAG Standard Specification, as modified below:

483.1 Description

The work under this section shall consist of furnishing and installing closed circuit television (CCTV) cameras at locations shown on the Plans.

483.2 Material

The CCTV Camera shall be Axis Communication model Q6042-E with a smoked dome.

The CCTV Camera cable shall be an outdoor rated CAT5e cable.

The CCTV Camera mounting bracket shall be Axis Communications model T-91A67.

The CCTV Camera surge protection shall be LCOM brand model HGLN-CAT5-HP or approved equal.

483.3 Construction Requirements

The new CCTV Camera shall be installed on traffic signal poles per TOQC Standard Details.  The CCTV Camera cabling shall run unspliced from the camera to traffic signal controller cabinet.  The CONTRACTOR shall deliver the CCTV Camera to the TOQC Traffic Department for configuration a minimum of 10 working days prior to installation.

After the CCTV Camera installation, the CONTRACTOR shall test to verify that the pan, tilt, zoom, and preset functions are performing properly.  The testing shall occur at both the local level, and from the TOQC Traffic Management Center (TMC)

483.4 Measurement

CCTV Camera Assembly will be measured for each camera system installed and tested to the TOQC approval.

483.5 Pavement

The accepted quantities of CCTV Camera Assembly, measured as provided above, will be paid for at the contract unit price for the type designated in the bidding schedule, complete in place including furnishing and installing CCTV camera cabling, mounting brackets, and surge protection.  No additional measurement or payment will be made for the testing of the CCTV Camera.

item 483.xxxxx	cctv camera assembly	ea

SECTION 485	VIDEO IMAGE DETECTORS

485.1 Description

The Contractor shall provide and install the video detection system, including system hardware and software.  The Contractor shall provide the cable from the pull boxes to the controller, and all equipment necessary for installing the video detection system as identified.  The Town of Queen Creek shall supervise the installation and testing of the video detection system and computer equipment. All Video Image Detector Systems must be on the Town of Queen Creek Approved Materials List.

Video detection cables shall run unspliced from the hand hole at each pole to the controller cabinet.  A manufacture supplied cable and pre-installed connector shall be supplied for connection to the back of the camera down the pole to the hand hole then spliced into the cable from the signal cabinet.  (Video detection splicing will on be allowed in the pole hand hole).  Contact the Town of Queen Creek for approved products.

Camera locations shall be coordinated with and approved by the Town.  Cost associated with this item shall include mounting brackets and necessary equipment and labor.

485.7 Payment

The accepted quantity of video detection system will be paid for at the contract unit price per each.  Such payment shall constitute full compensation for all labor, materials and equipment required for the furnishing, installation, testing and documentations.

item 485.xxxxx	Video Detection Systems (4 Camera System)	ea

# SECTION 486 COMMUNICATIONS EQUIPMENT

This section per the MCDOT supplement to the MAG Standard Specifications, as modified below:

486.1 Description

# The work under this section shall consist of furnishing and installing field hardened Ethernet switch and wireless radio/antenna system at locations shown on the Plans.

486.2 Materials

The field hardened Ethernet switch shall be Ruggedcom model #6GK6092-0PS23-0CA0-Z-A00-B00-C00-D00 with four single mode, 1300nm, 25km SFP’s (99-25-0101=1000LX SFP, Single mode, LC, 1310nm, 25km) with External power supply Ruggedcom RPS1300.

Gator Patch shall be Fiber Connections #G6XXJ012FRB-Y-Z 12 Fiber Gator Patch ITS drop cable.

486.3 Construction Requirements

The new field hardened Ethernet switch shall be installed in the traffic signal cabinet per TOQC Standard Details.  The installation shall be for ease of maintenance, with all component parts being readily accessible for inspection and maintenance.

The Contractor shall provide and install one CAT5e cable patch cord for connection between the Traffic signal controller and Ethernet switch.

The Contractor shall deliver the Ethernet switch and wireless radio/antenna to the TOQC Traffic Department for configuration a minimum of 10 working days prior to installation.

After the Ethernet switch installation, the contractor shall a test to verify the proper function of the network subsystem.  The traffic signal controller shall be tested for reliable communication between the TOQC TMC and the field device.  The communications shall be monitored for a 72 hour period for any communications failures or loss of data.

486.4 Measurement

Field hardened Ethernet switch will be measured for each Ethernet switch successfully installed and tested to the TOQC approval.

486.5 Payment

The accepted quantities of field hardened Ethernet switch, measured as provided above, will be paid for at the contract unit price for the type designated in the bidding schedule, complete in place including furnishing and installing camera cabling.

No additional measurement or payment will be made for conducting the network system testing.

item 486.xxxxx	FIELD HARDENED ETHERNET SWITCH	ea

item 486.xxxxx	wireless radio / atenna system	ea

item 486.xxxxx	gator patch	ea

PART 500 – STRUCTURES

SECTION 505 CONCRETE STRUCTURES

505.1 Description

Section 505.1 of the MAG Standard Specifications is modified to add the following:

All new storm drain manhole frames and covers shall be adjusted to grade according to MAG Standard Detail 422.  There shall be no additional payment for new storm drain manhole frame and cover adjustment.

All new storm drain manhole covers shall read “Queen Creek Storm Sewer.

No separate payment will be made for concrete pipe collars (MAG Standard Detail 505) and lateral pipe connections (MAG Standard Detail 524), the cost being considered incidental to the storm drain construction.

505.12 Payment

Section 505.12 of the MAG Standard Specifications is modified to add the following:

Payment for catch basins, scuppers, headwalls and spillways will be made at the contract unit price per each.

Safety rails with three-coat paint system shall be considered as included in the construction of drainage scuppers and no separate payment will be made for safety rails at scupper locations.

Concrete junction boxes shall be paid for at the unit price per each.

Such payment shall constitute full compensation for all of the work, materials, labor fabrication, hardware and incidentals associated with constructing said items complete in place.

ITEM 505.XXXXX	description	EA

SECTION 520	STEEL AND ALUMINUM HANDRAILS

520.1 Description

Section 520.1 of the MAG Standard Specifications is modified to add the following:

The plans identify handrails to be constructed at headwall locations. Handrails shall be painted, color to be approved by the Town of Queen Creek. The paint shall conform to the section below.

520.2 Fabrication and 530.9.1 Structural Steel

Add the following:

Steel handrail or safety rail per MAG Standard Detail 145, where not specified in the plans to be galvanized, shall be painted.  The paint system shall be a three-paint coating system in accordance with Arizona Department of Transportation (ADOT) Standard Specification 1002 and shall be listed on the ADOT Approved Product List in Category T-1 or T-2 or shall be an equal to the products so approved and listed.  The paint system shall consist of a primer coat, intermediate coat and top coat.  The primer shall not be applied over a galvanized metal surface.  All surface preparation shall be per specification and manufacturer’s recommendations.  The top coat paint shall have a semi-gloss or gloss finish. The top coat color shall be Federal Standard 595 Color FS 13578.  When matching newly painted surfaces to existing painted surfaces, a physical sample of the colored new paint system on a sample of the new substrate shall be provided to the Town Project Manager for comparison to the existing paint color to be matched.  Existing painted surfaces may have faded since application and may be lighter in color and less glossy than expected.  If an “equal to” paint system product is proposed, it shall be the responsibility of the CONTRACTOR and/or their vendor to supply sufficient product literature and technical data that shows the comparison to the approved product and specification with highlights, arrows, underlining or similar annotation for review by the Town Project Manager.  No separate measurement or payment shall be made for painting under this provision.  All materials, labor, tools, equipment and incidentals for painting shall be included in the unit price bid for the railing or bid item to which the railing is an included part.

SECTION 601 TRENCH EXCAVATION, BACKFILLING AND COMPACTION

601.4 Foundation, Bedding, Backfilling and Compaction

601.4.3 Backfill

The following is added:

No extra monetary compensation or additional time will be authorized for claims that soil conditions differ from those anticipated or those indicated by soil logs and/or reports.  It is the CONTRACTOR’s responsibility to make his own determination as to actual existing conditions.

601.4.4 Compaction Densities

The following is added:

Compaction densities for storm drain shall comply with Table 601-2 and Section 106.2.1 Samples of Tests and Materials in these special provisions.

SECTION 610 WATER LINE CONSTRUCTION

Add the following to MAG Standard Specifications Section 610.16:

610.2 General

Add the following:

All existing water pipelines requiring shut down in order to perform connections shall be scheduled to occur at night or weekends when affected businesses are closed.  All shut downs shall be restricted to between 10:00pm and 6:00 am.  With each shut down, the CONTRACTOR shall coordinate with the Town Fire Department to have a fire truck and personnel on standby at the project site or appropriate alternative measures in place.

All pipe shall be manufactured, handled, loaded and shipped, unloaded and stored a t the job site in such a manner as to prevent any damage to the pipe.  Any pipe section that becomes damaged shall be repaired as directed by the Town Utilities Department or Town Project Manager, if in his opinion a satisfactory repair can be made.  If the Town Utilities Department or Town Project manager determines repairs cannot be made, the material shall be replaced with undamaged materials at the CONTRACTORS’s expense.  No handling method will be permitted involving lifting for the inside of the pipe.

610.4 Construction Methods

Add the following:

Trenching shall comply with MAG Section 601 and adhere to maximum trench widths as defined in Table 601-1.

610.15 Testing

Add the following:

New waterlines shall be tested in accordance with Section 610.15 of the MAG Standard Specifications and the TOQC Water Utility Department “Design & Construction Standards Manual”.

610.19 Payment

Add the following:

Payment for water line and trench will be made at the contract unit price per linear foot.  Such payment shall constitute full compensation for all of the work associated with construction said items complete in place including fittings and coordination with the Town Fire Department.

item 610.XXXXX	Description	LF

Payment for fire hydrant will be at the contract unit price for the installation of each fire hydrant complete in place and in operating condition, including the 6 inch ductile iron pipe, valve, frame and cover; and fittings, required for making the  connection from the main to the hydrant , and shall constitute full compensation for furnishing all material, labor, tools and equipment and accomplishing all work associated with furnishing and installing the water pipe complete in place as described in the special provisions and on the construction plans.

item 610.XXXXX	fire hydrant assembly	ea

SECTION 618	IRRIGATION CONSTRUCTION

618.6 Payment

Section 618.6 of the MAG Standard Specifications is modified to add the following:

Payment for rubber gasket reinforced concrete pipe (RGRCP) will be made at the contract unit price per lineal feet, and shall constitute full compensation for furnishing all material, labor, tools and equipment and accomplishing all work associated with the furnishing and installing the fire hydrant complete in place as described in the special provisions and on the construction plans.

item 618.XXXXX	Description	LF

SECTION 619	STORM DRAIN CULVERTS

619.1 Materials

Section 618.6 of the MAG Standard Specifications is modified to add the following:

The allowable pipe material for storm drain pipe is rubber gasket reinforced concrete pipe.  For pipe classes, see the Plans.

619.2 Payment

Section 618.6 of the MAG Standard Specifications is modified to add the following:

Payment for storm drain pipe shall include concrete pipe collars (MAG Standard Detail 505) and lateral pipe connections (MAG Standard Detail 524) as specified on the plans; no separate payment will be made for concrete pipe collars and lateral connections.

Payment for storm drain pipe will be made at the contract unit price per linear foot, and shall constitute full compensation for furnishing all material, labor, tools and equipment and accomplishing all work associated with the furnishing and installing the pipe complete in place as described in the special provisions and on the construction plans.

item 619.XXXXX	description 	LF

SECTION 631 WATER METER AND METER SERVICE CONNECTIONS

631.1 Description

Section 631.1 of the MAG Standard Specifications is modified to add the following:

Water service taps shall not be completed until the new waterlines have been tested and accepted by the Town.